## Sheet1
BOQ for upgraded one Hand Pump to Mini Water Yard in
Item | Description | Unit | Quantity | Unit Rate SDG | Cost
1 | Site preparation
1.1 | Cleaning the site from grass and removal of rubbish and level the ground | Job | 1 | 50000 | 50000
2 | Digging the holes for fencing and install the fencing
2.1 | Digging 37 holes 40 x 40 50 cm to install the 1'' galvanize pipe | m3 | 3 | 2500 | 7500
2.1 | Install 1 '' 3 meters steel galvanize pipe 0.5 m in the holes and 2.5 above the ground, fill it with concrete and small pices of stons. Mix 1:3:6 based on design | m3 | 3 | 25000 | 75000
2.3 | Galvanize steel pipe 1 inch diameter with 2 mm tickness and 6 meters length | Pcs | 19 | 7000 | 133000
2.4 | Galvanize Mesh rolls with 2 inches opennig, 2 meters wide and 10 meters length | Roll | 6 | 15000 | 90000
2.5 | 2 mm tickness wire to be connected to steel pipe all around to install the mesh and hold them stady | m | 280 | 1000 | 280000
2.6 | Tie wire to connect the mesh to steel pipe and the 2 mm wire | Kg | 10 | 1500 | 15000
2.7 | Strong steel door with strong frame based on design | Pcs | 1 | 35000 | 35000
3 | Hand pump needs to convert to MWY
3.1 | Galvanize 2 inches pipe each 3 meters length | Pcs |  |  | 0
3.2 | Connection for 2 inches pipe | Pcs |  |  | 0
3.3 | Supply and install complete 1.5 HP solar submersible pump, includeing all necessary accessories and electrical standdard cables and wries | Pcs | 1 | 900000 | 900000
3.4 | Solar Panels for 1.5 HP submersible pump, 300 W each | Pcs | 10 | 2500 | 25000
3.5 | Strong steel structure with Angel shape steel 2''x2'' with 2 mm tickness including anti rust and three coats of oil paint to hold 10 solar panels. | LS | 1 | 65000 | 65000
3.6 | DC-DC converter for 1.5 HP submersible pump | Pcs | 1
3.7 | DC-AC Inverter for 1.5 HP submersible Pump | Pcs | 1
3.8 | Conduct Opration Test for 2 days (under MC Engineer suppervision) | LS | 1 | 600000 | 600000
4 | Elevated water tank
5 | Room
15 | Supply materials and build a drainage system | job | 1 | 150000 | 150000
18 | Supply and install sign board of MC and USIAD logos | pcs | 1 | 50000 | 50000
| TOTAL in SDG |  |  |  | 2475500
| Total in USD |  |  |  | 5451.5361

## Altoub Ala MWY_Alrahad Locality
Mercy Corps - Gadarif State Office
BHA Project:33657 Date: 4/10/22
Bills of Quantities for Upgrading of Hand Pump to Mini Water Yard
Project name: Upgrading of Altoub Alahmer Hand Pump to Mini Water Yard
Project Location: Altoub Alahmer Village - Alrahad Locality - Gedaref State
GPS N 13° 06' 27.8.1" E 034° 56' 28.0"
Item | Description | Unit | Quantity | Unit Rate | Total amount
|  |  |  | SDG | SDG
1 | Site Preparation
1.1 | Mobilization: This item include physical mobilization of the equipment, construction materials & manpower. | Job | 1
1.2 | Site cleaning and levelling: Cleaning the site from grass and removal of rubbish and level the ground | Job | 1
2 | Foundation for elevated water tank
2.1 | Digging the trench for foundation 3.5 x 3 m, 13 x 0.4 x 0.7 m | M3 | 3.5
2.2 | filled the foundtaion with stone and martor 1:6 up to 70 cm ground level. | M3 | 3.5
3 | Grade beam
3.1 | Grade beam all over the top of foundation from with 13 x 0.40 x 0.30 m with reinforce concrete based on design and cure that for three days ( everyday 6 times). This job include labor, materials and necessary tools. | M3 | 2
4 | Brick walls
4.1 | Raise the walls from the top of grade beam up to 2.5 meters with one and half bricks (30 cm) and martor 1:6, this include labor, and materials, water and tools | M2 | 25
4.2 | Plastering both sides smoothly, including labor, materials, water and tools, mix 1:6 | M2 | 50
4.3 | Bomastic painting, three coats | Gallons | 5
5 | Floor:
5.1 | Lay the excavated siol on the floor and compact it 15 cm, then 15 cm with gravel and small piecs of stonses, and the last 10 cm with plain concrete mix 1:3:6, | M3 | 2
6 | Ring beam
6.1 | Reinforce concrete ring beam all over the top of brick walls, 0.30 x 0.20. mix 1:2:4, include labor, materials water and tools | M3 | 1
7 | Slab Concrete
7.1 | Reinforce salb concrete with 10 cm depth and the rebars should be connect to ring beam rebars . mix 1:2:4, include labor, materials water and tools | M3 | 1
8 | Provision and installation of Solar system & Submersible pump
8.1 | Supply and install complete 1.5 HP solar submersible pump, includeing all necessary accessories and electrical standard cables, wries and connection to control panel. The price is inclusive of removing existing water hand pump and inspection the well casing and filters status. | Unit | 1
8.2 | Gl pipes (Delivery pipe): Supply and install Galvanize pipe 1.5 inches Dim, 3 meters length with connection fittings. | No | 12
8.3 | Supply and installation of Solar Panels to cover the load of 1.5 HP submersible pump, 400 W each. | No | 10
8.4 | Steel stands for the solar panels: Provision of materials and fabrication of strong steel stand structure with Angel shape steel 2''x2'' with 2 mm tickness including anti rust and three coats of oil paint to hold 10 solar panels. Concrete for 12 holes with (40*40*50cm), including labor | Job | 1
8.5 | Supply and installation of DC-DC converter for 1.5 HP submersible pump, with all accessories . | No | 1
8.6 | Supply and installation of DC-AC Inverter for 1.5 HP submersible Pump, with all accessories. | No | 1
8.7 | Supply and installation of 4 batteries each 200 A | Pcs | 4
8.8 | Conduct Opration Test for 2 days (under MC Engineer suppervision) | LS | 1
9 | Water Tank:
9.1 | Supply & erect 5000 L capacity, plastic cylindrical storage water tank (Tiga),mounted on a 2.5-meters high tower construct of bricks and concrete. The price is inclusive of all necessary fittings, valves, connection and piping, all according to technical specifications attached and the directions of the Engineer. | pcs | 1
9.2 | Doors, two steel doors 1 x 1.9 m, including anti rust and three coat of oil paint | pce | 2
10 | Distribution System (Pipe Works):
10.1 | Supply and fix 1.5" Gl pipes from the well to the elevated water tank including all necessary fittings. | ml | 10
10.2 | Supply and fix 1.5" GL pipes from the elevated water tank to distribution point including all necessary fittings. | ml | 30
10.3 | Supply and install 1.5" non-return valve at the water tank inlet including all necessary fittings. | No | 1
10.4 | Supply and install 1.5" valve at the elevated water tank outlet pipes including all necessary fittings. | No | 2
11 | Water Disrubuation Points
11.1 | Disrubuaion Point: Construct distribuation point 1.7 including foundation × 1.2 m high, foundation with stones and martor and top structure with bricks and martor, plus plastering both sides mix (1:6) . The price is inclusive of (1") GL pipe with 8 pressed taps 1 /2" all necessary materials, labor, tools drainage system. plus one truck 10 cubic meters of gravel for around the water point. All the works should be complete according to specifications, design and the directions of the Engineer. | LS | 1
11.2 | Construct a collection water storage at the end of drainage channel of distribution point away from the MWY (10m at least) for animal to drink the waste water by 1*1*0.5 m depth, by one brick wall with mortar cement 1:8 plus plaster inside wall 1:6 , add 10 cm concrate in the bottom ,Include labos and materials (cement,bricks,water, sand) | LS | 1
12 | Fence & Gate
Provision of materials and installation of fence for the mini water yard, all according to specifications bellow and the directions of the Engineer:
12.1 | Digging 38 holes 40 x 40 x 50 cm to install the 2'' galvanize steel pipes | m3 | 3
12.2 | supply and installation 2" circular steel pipes 2.5m length and 2mm thickness painted with silver color paint, spaced at 2 m distances with 2 mm galvanized wire welded (at top, bottom and the middle). | pcs | 38
12.3 | The 2" circular steel pipes should erect in 0.5 m depth in the holes and 2.0m above the ground, fill it with concrete and small pices of stons. Mix 1:3:6 based on design | m3 | 3
12.4 | Galvanize Mesh rolls, gabion wire (class A) with 2 inches opennig, 2 meters wide and 10 meters length. 2 mm tickness wire to be connected to steel pipe all around to install the mesh and hold them stady | ml | 70
12.5 | Fence corners should be supported with 2-inch strainer-angled ion. | pcs | 4
12.6 | Provide and erect fence gate made of two leafs of steel angle 3 ", 3m wide for the mini water yard as per design. | No | 1
13 | Signboard:
13.1 | Supply and install steel project sign board of MC and USIAD logos, writing and drawing as per drawings, specifications and the directions of the Engineer. | pcs | 1
14 | Demobilization: of equipment and personnel from site including cleaning the site from derbies and reinstatement to its original condition. | Job | 1
| Total cost in SDG |  |  | 0 | 0
| VAT 17% |  |  |  | 0
| Grand Total |  |  |  | 0

## Sharab MWY_Alfaw Locality
Mercy Corps - Gadarif State Office
BHA Project:33657 Date: 4/10/22
Bills of Quantities for Upgrading of Hand Pump to Mini Water Yard
Project name: Upgrading of Sharab Hand Pump to Mini Water Yard
Project Location: Sharab Village - Alfaw Locality - Gedaref State
GPS N 14° 02' 49.5" E 033° 59' 23.4"
Item | Description | Unit | Quantity | Unit Rate | Total amount
|  |  |  | SDG | SDG
1 | Site Preparation
1.1 | Mobilization: This item include physical mobilization of the equipment, construction materials & manpower. | Job | 1
1.2 | Site cleaning and levelling: Cleaning the site from grass and removal of rubbish and level the ground | Job | 1
2 | Foundation for elevated water tank
2.1 | Digging the trench for foundation 3.5 x 3 m, 13 x 0.4 x 0.7 m | M3 | 3.5
2.2 | filled the foundtaion with stone and martor 1:6 up to 70 cm ground level. | M3 | 3.5
3 | Grade beam
3.1 | Grade beam all over the top of foundation from with 13 x 0.40 x 0.30 m with reinforce concrete based on design and cure that for three days ( everyday 6 times). This job include labor, materials and necessary tools. | M3 | 2
4 | Brick walls
4.1 | Raise the walls from the top of grade beam up to 2.5 meters with one and half bricks (30 cm) and martor 1:6, this include labor, and materials, water and tools | M2 | 25
4.2 | Plastering both sides smoothly, including labor, materials, water and tools, mix 1:6 | M2 | 50
4.3 | Bomastic painting, three coats | Gallons | 5
5 | Floor:
5.1 | Lay the excavated siol on the floor and compact it 15 cm, then 15 cm with gravel and small piecs of stonses, and the last 10 cm with plain concrete mix 1:3:6, | M3 | 2
6 | Ring beam
6.1 | Reinforce concrete ring beam all over the top of brick walls, 0.30 x 0.20. mix 1:2:4, include labor, materials water and tools | M3 | 1
7 | Slab Concrete
7.1 | Reinforce salb concrete with 10 cm depth and the rebars should be connect to ring beam rebars . mix 1:2:4, include labor, materials water and tools | M3 | 1
8 | Provision and installation of Solar system & Submersible pump
8.1 | Supply and install complete 1.5 HP solar submersible pump, includeing all necessary accessories and electrical standard cables, wries and connection to control panel. The price is inclusive of removing existing water hand pump and inspection the well casing and filters status. | Unit | 1
8.2 | Gl pipes (Delivery pipe): Supply and install Galvanize pipe 1.5 inches Dim, 3 meters length with connection fittings. | No | 12
8.3 | Supply and installation of Solar Panels to cover the load of 1.5 HP submersible pump, 400 W each. | No | 10
8.4 | Steel stands for the solar panels: Provision of materials and fabrication of strong steel stand structure with Angel shape steel 2''x2'' with 2 mm tickness including anti rust and three coats of oil paint to hold 10 solar panels. Concrete for 12 holes with (40*40*50cm), including labor | Job | 1
8.5 | Supply and installation of DC-DC converter for 1.5 HP submersible pump, with all accessories . | No | 1
8.6 | Supply and installation of DC-AC Inverter for 1.5 HP submersible Pump, with all accessories. | No | 1
8.7 | Supply and installation of 4 batteries each 200 A | Pcs | 4
8.8 | Conduct Opration Test for 2 days (under MC Engineer suppervision) | LS | 1
9 | Water Tank:
9.1 | Supply & erect 5000 L capacity, plastic cylindrical storage water tank (Tiga),mounted on a 2.5-meters high tower construct of bricks and concrete. The price is inclusive of all necessary fittings, valves, connection and piping, all according to technical specifications attached and the directions of the Engineer. | pcs | 1
9.2 | Doors, two steel doors 1 x 1.9 m, including anti rust and three coat of oil paint | pce | 2
10 | Distribution System (Pipe Works):
10.1 | Supply and fix 1.5" Gl pipes from the well to the elevated water tank including all necessary fittings. | ml | 10
10.2 | Supply and fix 1.5" GL pipes from the elevated water tank to distribution point including all necessary fittings. | ml | 30
10.3 | Supply and install 1.5" non-return valve at the water tank inlet including all necessary fittings. | No | 1
10.4 | Supply and install 1.5" valve at the elevated water tank outlet pipes including all necessary fittings. | No | 2
11 | Water Disrubuation Points
11.1 | Disrubuaion Point: Construct distribuation point 1.7 including foundation × 1.2 m high, foundation with stones and martor and top structure with bricks and martor, plus plastering both sides mix (1:6) . The price is inclusive of (1") GL pipe with 8 pressed taps 1 /2" all necessary materials, labor, tools drainage system. plus one truck 10 cubic meters of gravel for around the water point. All the works should be complete according to specifications, design and the directions of the Engineer. | LS | 1
11.2 | Construct a collection water storage at the end of drainage channel of distribution point away from the MWY (10m at least) for animal to drink the waste water by 1*1*0.5 m depth, by one brick wall with mortar cement 1:8 plus plaster inside wall 1:6 , add 10 cm concrate in the bottom ,Include labos and materials (cement,bricks,water, sand) | LS | 1
12 | Fence & Gate
Provision of materials and installation of fence for the mini water yard, all according to specifications bellow and the directions of the Engineer:
12.1 | Digging 38 holes 40 x 40 x 50 cm to install the 2'' galvanize steel pipes | m3 | 3
12.2 | supply and installation 2" circular steel pipes 2.5m length and 2mm thickness painted with silver color paint, spaced at 2 m distances with 2 mm galvanized wire welded (at top, bottom and the middle). | pcs | 38
12.3 | The 2" circular steel pipes should erect in 0.5 m depth in the holes and 2.0m above the ground, fill it with concrete and small pices of stons. Mix 1:3:6 based on design | m3 | 3
12.4 | Galvanize Mesh rolls, gabion wire (class A) with 2 inches opennig, 2 meters wide and 10 meters length. 2 mm tickness wire to be connected to steel pipe all around to install the mesh and hold them stady | ml | 70
12.5 | Fence corners should be supported with 2-inch strainer-angled ion. | pcs | 4
12.6 | Provide and erect fence gate made of two leafs of steel angle 3 ", 3m wide for the mini water yard as per design. | No | 1
13 | Signboard:
13.1 | Supply and install steel project sign board of MC and USIAD logos, writing and drawing as per drawings, specifications and the directions of the Engineer. | pcs | 1
14 | Demobilization: of equipment and personnel from site including cleaning the site from derbies and reinstatement to its original condition. | Job | 1
Total cost SDG
Vat 17%
Grand Total