## Guli Jaleen Hafir Rehabilitatio
Annex 7C- Guli haffir
BOQ for Guli Algaleen Hafir Rehabilitation
Item | Specifications | Unit | Quantity | Unit Price | Cost SDG | Cost USD
1. Inlet & Outlet System |  |  |  |  | 0 | 0
1.1 | Rehabilitate the existing inlet and outlet wells (2 inlet & 1 outlet). Rehabilitation work include: (cleaning of wells by removing silt from inlet and stones from outlet, fixing of outletcover, checking of inet and outlet pipe, etc.) | job | 1
2. Fence Rehabilitation |  |  |  |  | 0 | 0
Rehabilitate the existing fence of hafir, the fence made of steel angle 3", 5mm in distance of 2.0 m and barbed wire 7 line horizental, and verticl in space of 25 cm, distance 1260m, hight 1.5m. The rehabilitation work as the following: |  |  |  |  | 0 | 0
2.1 | Provide material and erect new fence as the specification above, needs new barbed wire and fixing of existing angles in concrete fondation 40x40x50cm. | m.l | 330
2.2 | Provide material and fix in concrete fondation 40x40x50cm 3" steel angle 5mm thickness, 2.0 m length (1.5m above the ground), the price include fixing of barbbid wire on the angles. | No | 40
2.3 | Gate size (3.0m x 1.50m) consists of tow leaf. External frame from steel box section 4x8 cm and internal frames of steel box section 3x6 cm. Leaf filling is with steel sections 2x4cm vertically and horizontally each 15cm. Gate supports are from steel sections 5x10 cm fixed on plain concrete footing (0.50m x 0.50m x 0.60m). All steel sections must be painted with red-oxide paint and 2 coats of approved oil paint. | Job | 1
2.4 | Gate size (1.5m x 1.50m) consists of one leaf. External frame from steel box section 4x8 cm and internal frames of steel box section 3x6 cm. Leaf filling is with steel sections 2x4cm vertically and horizontally each 15cm. Gate supports are from steel sections 5x10 cm fixed on plain concrete footing (0.50m x 0.50m x 0.60m). All steel sections must be painted with red-oxide paint and 2 coats of approved oil paint. | Job | 1
2.5 | Supply, excavate and fix chain-link fence with following specifications: Supports are from 2" circular steel pipes of 1.2mm thickness and height not less than 1.5 m above ground, fixed in plain concrete (1:2:4) footing size (0.40m x 0.40m x 0.50m). 2.8 mm Chain-link is fixed on the supports Three 12mm steel bars are to be provided at top, middle and bottom of fence according to drawings. Struts are to be made of 2½” steel angles at corners according to drawings. | ml | 100
Total
VAT 17%
Grand Total

## Roro Hafir Rehabilitation
ANNEX 7 B- Roro Haffir
BOQ for Roro Hafir Rehabilitation
Item | Specifications | Unit | Quantity | Unit Price | Cost SDG | Cost USD
1. Inlet & Outlet System |  |  |  |  | 0 | 0
1.1 | provide material and lay 12" UPVC pipe 10 bar to connect hafirs, the price include excavation between hafirs for pipe as the instructions of engineer | ml | 70
1.2 | Construction of inlet well, well internal diameter 3m, wall thickness 0.3m and hight 2m. |  |  |  | 0 | 0
1.3 | Provide material and cast in position 0.2m thickness, R/C 1:2:4 for well base slab.. | m3 | 2
1.4 | Provide material and build in masonry or brick for the wall in 1:4 s/c mortar, wall thickness 0.3 m and well hight 2m. | m2 | 20
1.5 | Provide material and lay 1nlet pipe 12'' UPVC pipe 10 bar, the price include excavation of pipe trench. | ml | 42
1.6 | Provide materials manufacture and fix a circular grill on the top of the in let well the grill from angled iron 2'' and mild steal rod 1/2'' as shown in the drawing to prevent entrance of broken woods and bushes to get inside the inlet pipes. | No | 2
2 | Construction of outet well, well intenal diameter 3m, wall thickness 0.3m and hight 5m. |  |  |  | 0 | 0
2.1 | Provide material and cast in position 0.2m thickness, R/C 1:2:4 for well base slab.. | m3 | 2
2.2 | Provide material and build in masonry or brick for the wall in 1:4 s/c mortar, wall thickness 0.3 m and well hight 2m. | m2 | 50
2.3 | Provide material and lay outlet pipe 8'' UPVC pipe 10 bar, the price include excavation of pipe trench. | ml | 60
2.4 | Provide materials and construct with stone and mortar pitching around the out well | m3 | 15
3. Chain-link Fance |  |  |  |  | 0 | 0
3.1 | Supply, excavate and fix chain-link fence with following specifications: Supports are from 2" circular steel pipes of 1.2mm thickness and height not less than 1.5 m above ground, fixed in plain concrete (1:2:4) footing size (0.40m x 0.40m x 0.50m). 2.8 mm Chain-link is fixed on the supports Three 12mm steel bars are to be provided at top, middle and bottom of fence according to drawings. Struts are to be made of 2½” steel angles at corners according to drawings. | ml | 1000
3.2 | Gate size (2.50m x 1.50m) consists of tow leaf. External frame from steel box section 4x8 cm and internal frames of steel box section 3x6 cm. Leaf filling is with steel sections 2x4cm vertically and horizontally each 15cm. Gate supports are from steel sections 5x10 cm fixed on plain concrete footing (0.50m x 0.50m x 0.60m). All steel sections must be painted with red-oxide paint and 2 coats of approved oil paint. | job | 1
Total
VAT 17%
Grand Total

## Agadi Hafir Rehabilitation
ANNEX 7A- Agadi Haffir
BOQ for Agadi twin Hafir Rehabilitation
Item | Specifications | Unit | Quantity | Unit Price | Cost SDG | Cost USD
1. Inlet & Outlet System |  |  |  |  | 0 | 0
1.1 | Construction of inlet well, well internal diameter 3m, wall thickness 0.3m and hight 2m. |  |  |  | 0 | 0
1.1 | Provide material and cast in position 0.2m thickness, R/C 1:2:4 for well base slab.. | m3 | 2
1.2 | Provide material and build in masonry or brick for the wall in 1:4 s/c mortar, wall thickness 0.3 m and well hight 2m. | m2 | 20
1.3 | Provide material and lay 1nlet pipe 12'' UPVC pipe 10 bar, the price include excavation of pipe trench. | ml | 60
1.4 | Provide materials manufacture and fix a circular grill on the top of the in let well the grill from angled iron 2'' and mild steal rod 1/2'' as shown in the drawing to prevent entrance of broken woods and bushes to get inside the inlet pipes. | No | 2
2 | Construction of outet well, well intenal diameter 3m, wall thickness 0.3m and hight 5m. |  |  |  | 0 | 0
2.1 | Provide material and cast in position 0.2m thickness, R/C 1:2:4 for well base slab.. | m3 | 2
2.2 | Provide material and build in masonry or brick for the wall in 1:4 s/c mortar, wall thickness 0.3 m and well hight 2m. | m2 | 50
2.3 | Provide material and lay outlet pipe 8'' UPVC pipe 10 bar, the price include excavation of pipe trench. | ml | 60
2.4 | Provide materials and construct with stone and mortar pitching around the out well | m3 | 15
3. Chain -link Fence |  |  |  |  | 0 | 0
3.1 | Supply, excavate and fix chain-link fence with following specifications: Supports are from 2" circular steel pipes of 1.2mm thickness and height not less than 1.5 m above ground, fixed in plain concrete (1:2:4) footing size (0.40m x 0.40m x 0.50m). 2.8 mm Chain-link is fixed on the supports Three 12mm steel bars are to be provided at top, middle and bottom of fence according to drawings. Struts are to be made of 2½” steel angles at corners according to drawings. | ml | 1050
3.2 | Gate size (2.50m x 1.50m) consists of tow leaf. External frame from steel box section 4x8 cm and internal frames of steel box section 3x6 cm. Leaf filling is with steel sections 2x4cm vertically and horizontally each 15cm. Gate supports are from steel sections 5x10 cm fixed on plain concrete footing (0.50m x 0.50m x 0.60m). All steel sections must be painted with red-oxide paint and 2 coats of approved oil paint. | job | 2
Total
VAT 17%
Grand Total