## Detailed Evaluation
Technical Evaluation Scoring Matrix
Evaluation Factors | Max Scores Allocated | A | B | C | D | E | F | Line Comments
Mandatory
Valid Registration Documents / Certificate issued by competent authority | PASS/FAIL (failing to meet a single mandatory criterion will result in disqualification of the contractor from further technical evaluation)
Company Age Not less than 3 years from the date of registration / incorporation
Bidder confirms the acceptance of the following in writing and will be required to strictly adhere to; for the purpose of the proposed contract. UNHCR General Conditions of Contracts for Civil works (Annex E) UNHCR General Conditions of Contracts for the Provision of Services (Annex F) UN suppliers code of conduct (Annex G)
Scoring Criteria
Responsiveness to RFP (0-5) marks | Required Parameters: 1. Understanding of, and responsiveness to, UNHCR requirements. 2. Understanding of scope, objectives and completeness of response. 3. Overall concord between UNHCR requirements and the proposals. ______________________________ a. Full understanding of UNHCR requirements: the proposal made by the bidder is complete and is fully responsive based on above parameters = 5 b. To a larger extent understands UNHCR requirements and the proposal made by the bidder is complete and is mostly responsive based on above parameters = 3 c. Does not understand UNHCR requirements and the proposal made by the bidder is not complete and is not responsive based on above parameters = 0
Total= 05 Marks
Technical approach and methodology (0-10) marks | Mobilization time= 5 Marks (1- 15) Days = 5 Marks (15 - 20) Days = 4 Marks (20 - 25) Days = 2 (25 updwards) Days = 1
Monitoring and Reporting Proposed Reporting Mechanism on weekly basis = 5 Marks Proposed Reporting Mechanism on bi-weekly basis = 3 Marks Proposed Reporting Mechanism on monthly basis = 1 Marks
Total= 10 Marks
Construction Management Plan (0-10) marks | Quality of Work Schedule Charts= 5 Marks
Proposed works completion time is reasonable = 5 marks
Proposed works completion time is fairly reasonable = 3 - 4 Marks
Prposed works completion time is unreasonable= 0 - 2 Marks
Total= 10 Marks
Relevant Experience of Firm (0-30) marks | Total building construction projects undertaken (two marks for each project up to maximum 10 marks)
No. of signature building projects undertaken in Darfur (two marks for each project up to maximum 10 marks)
No of building constrcution propjects undertaken for the UN, Embassies or other international organisations (two marks for each project up to maximum 10 marks)
Total= 30 Marks
Resident Engineer (Buildings 1 No. (0-15) marks | B.Sc. Eng. + 5 years= 13 Marks
M.Sc. Eng. + 2 years=13 Marks
Additional years of experience 2 Mark
Total=15 Marks
Asst. Resident Engineer (Buildings/Structure) 1 No. (0-10) marks | B.Sc. Eng. +3 years= 8 Marks
M.Sc. Eng. + 1 years=8 Marks
Additional years of experience 2 Mark
Total=10 Marks
Quantity Surveyors- 1 No. (0-5) marks | Diploma + 2 years=3 Marks
Diploma + 5 years or B.Sc.=4 Marks
Additional years of experience 1 Mark
Total=05 Marks
Annual Turn over- (0-15) (within past five years) | Annual turn over up to USD 70,000 = 5 marks
Annual turn over up to USD 80,000 = 10 marks
Annual turn over up to USD 90,000 or above= 15 marks
Total=15 Marks
Total Marks (100)
Technical part is 60%. A minimum of 60 marks/100 is required to qualify for financial evaluation.
Ranking
Overall Comments