## Sheet1
Workplan for construction of SAFE program stores
Contractor: |  |  |  | Store Location:
Project site location: … …………….……………. |  |  | March
| Description of work | Duration required for the activity-in Days | 1st - -7th | 8th - - 14th | 15th - - 21th | 22th - - 30th
1 | Mobilization of material & workers
2 | Excavation & stone pitching
3 | Tie beam (Reinforce Concrete)
4 | Brick & Masonry Work up to Ring beam
5 | Ring Beam (all over the walls at 2.4 meter high)
6 | Brick & Masonry Work above the ring beam
7 | Floor (Backfilling and Concrete)
8 | Door & Windows Fixing
9 | Roofing work
10 | Plastering And Painting
Workplan for construction of SAFE program stores
Contractor: |  |  |  | Store Location:
Project site location: … …………….……………. |  |  | March
| Description of work | Duration required for the activity-in Days | 1st - -7th | 8th - - 14th | 15th - - 21th | 22th - - 30th
1 | Mobilization of material & workers
2 | Excavation & stone pitching
3 | Tie beam (Reinforce Concrete)
4 | Brick & Masonry Work up to Ring beam
5 | Ring Beam (all over the walls at 2.4 meter high)
6 | Brick & Masonry Work above the ring beam
7 | Floor (Backfilling and Concrete)
8 | Door & Windows Fixing
9 | Roofing work
10 | Plastering And Painting
Workplan for construction of SAFE program stores
Contractor: |  |  |  | Store Location:
Project site location: … …………….……………. |  |  | March
| Description of work | Duration required for the activity in Days | 1st - -7th | 8th - - 14th | 15th - - 21th | 22th - - 30th
1 | Mobilization of material & workers
2 | Excavation & stone pitching
3 | Tie beam (Reinforce Concrete)
4 | Brick & Masonry Work up to Ring beam
5 | Ring Beam (all over the walls at 2.4 meter high)
6 | Brick & Masonry Work above the ring beam
7 | Floor (Backfilling and Concrete)
8 | Door & Windows Fixing
9 | Roofing work
10 | Plastering And Painting