## Bid Offer Sheet
Price Offer Sheet (Intended as a guide. Please modifiy and/or add additional lines as needed.)
Item Description | Quantity | Unit of Measure | Unit Price | Total Price
1. Hold consultations with farmers, associations, and cooperatives to determine needs. What subject matter is most needed by them. Consultations should involve youth and women to ensure inclusivity and relevance of topics to them.
A. Information gathering with stakeholders to identify gaps between exisiting platform and enhancements needed
B. Reporting on gap analysis written.
2. Hold meetings with other SASAS project partners and private sector companies to determine if they have relevant content that can be incorporated into the Hotline. (Mercy Corps has entered or is in the process of entering into agreements with companies such as seed companies, produce buying companies, and banks/ MFIs to promote development of the agriculture sector and increase productivity smallholder farmers. These partnerships complement each other and improve outcomes for business and farmers. The provider of the Hotline may be able to incorporate content these providers have if it is deemed relevant.)
A. Meetings held with agreed partners and summary report of 2-3 pages in length written for each meeting.
B. Overall summary report of all meetings held with recommendations for possible inclusion in Hotline
2. Curate and/or develop pre-recorded content (in Arabic) on agricultural advisory topics. This should be guided by the needs determined in point “1 and 2” above. It is expected topics such as improved seeds, planting techniques, crop rotation, pesticide and fertilizer application, post-harvest handling and animal health would be among them.
A. Content drafted, reviewed and agreed for inclusion in Hotline
B. Test content accessibility
3. Publicize and promote the Hotline service and deploy the service to farmers and farmer groups, through means such as meetings, sensitizations, promotions, advertisements etc.
A. Promote the Hotline via various forms of media (radio, adverts, attendance at seed fairs, etc.)
B. Enroll 2000 Hotline users
C. Strategy plan for female inclusion
4. Provide ongoing support to the Hotline and implement improvements to increase adoption and uptake by targeted audiences.
5. Provide a feedback mechanism for users of the Hotline to respond to their questions and the overall user experience.
6. Provide reporting and analytics showing Hotline participation numbers by age, gender, feature, time of day, etc. to allow for refinement of the user experience and topics of interest.
A. Monthly report prepared and distributed.
7. Add to the Hotline Facebook and/or WhatsApp coupling with Chat box functionality to allow information in different multimedia formats (video, images, audio, etc.) to be targeted to those with smartphones
Total before tax:
VAT (if applicable)
Total:
Company Name:
Name of Representative:
Title:
Signature:
Date:
Tender #: SKS-1504 seed companies to establish and/or expand seed sales agent networks, carry out seed sales promotions and sell seeds at a discounted price to smallholder farmers in South Kordofan State. Seeds include Sorghum, Groundnut, Sesame and a variety of vegetables. SASAS Program (Sustainable Agrifood Systems for Sudan)