## Scope of work
Minor repair and maintenance of four health facilities -Blue Nile
Painting works of the wall as per specifications and Engineer's site instruction
Other very minor repair works as per Engineers site instruciton
Maintenance of CMAM sites including SC in Madina 10-Blue Nile
Conduct essential demolishing, excavation and backfilling work.
Painting work of the wall as per specifications and Engineer's instruction
Concrete work of the CMAM rooms floor as per specifications
Hand pumps rehabilitations -Blue Nile
Transportation and storage of all required material, equipment and labour to site.
Conduct assessemnt of the non-functional Handpump and identify the problem
Dismantling of the raiser main, connecting rod, cylinder and other accessories
Replacement of the defected Handpump components/the whole handpump when needed with new one
Re-installation of the handpump and riser main
Shock chlorination and pumping of the handpump for 45minutes
Deploying all Labour, equipment and material needed for the rehabilitation
Pipeline extension for HF-Blue Nile
Transportation and storage of all required material, equipment and labour to site.
Pipeline trench excavation should be atleast 0.6 meter depth at to avoid any damange on pipes
Vendor should use appropriate type of pipe and fittings approved by supervisor Engineer
Vendor need to make pipeline connection properly to avoid any leakage issues.
Operate the pipeline to test smooth operation, leakage and pressure.
Handwashing facility- Blue Nile
Assembling and installing of the Handwashing metal stand with high quality metal with specification approved by RI
Installing of water storage tank of appropriate size approved by RI
Installing of appropriate quality fittings approved by RI
Painting of anti-rust paint
Transportation of the Handwashing facilities to the target Health facilities as per distribution plan of RI
Rehabilitation of Alwehida Geissan HF latrine-Blue Nile
Conduct essential demolishing, excavation and site clearing work around the collapsed pit wall and top cover
Reconstruct the collapsed pit wall and cover and connect properlly with the existing wall structure
Conduct essential back filling and land scaping work
Carryout essential maintenance work of the part of the latrine wall
Construct disability access(both concrete ramp and metal support) as per the specification and Engineer's site instruction
Minor repair and maintenance of CMAM sites-Blue Nile
Minor demolishing , excavation and backfilling works as need and as per Engineer's instruction
Minor concrete repair and maintenance works.
Minor brick wall repair and maintenance works.
repair and fixing of metal elements including doors and locks.
Other minor repair works as per Engineers site instruciton
Major repair and maintenance of CMAM sites-Blue Nile
Transportation and storage of all required material, equipment and labour to site.
Carryout essential demolishing and/or excavation works as needed and as per Engineers instruction
Carryout concrete construction works as per specifications and Engineers instruction
Painting works and fixing of metal elements including door as per specifications and Engineer's instruction
Carryout other minor maintenance works as per Engineer's instruction
Ashpit construction for Incinerator-Blue Nile
Transportation and storage of all required material, equipment and labour to site.
Excavation of the Ashpit with a dimention of 3mx2mx2m
Construction of foundation concrete of thickness 15cm
Construction of brick pit wall in all sides of the pit as per Engineer's instruction.
Construction of the Ash pit cover according to drawing and specifications
Supply and installation of the manhole cover for the Ashpit cover.
Other finishing works as per need and Engineers instruction
Incinerator Constuction with fence-Blue Nile
Transportation and storage of all required material, equipment and labour to site.
Apply standard fire bricks of high quality & adequate quantity approved by RI for the construction purpose
Constructing the brick work according to the drawing and specifications
All metal works and welding should be upto standard and with RI approved specifications
Vendor should test the Incinerator after construction with burning of medical waste to check performance and any visible crack
Elevated tank with pumping and pipeline connection-Blue Nile
Transportation and storage of all required material, equipment and labour to site.
Construction of elevated tank stand with metal of the required quality and RI approved specifications
Installing of 2000liter water tank with required quality and RI approved specifications
Installing of all needed pipes, fittings, surface pump, Generator/solar and other accessories with the required quality and RI approved specifications
Test the system for smooth operation and leakage