**Term of Reference, Labor Market & Energy Need Assessment and selection of beneficiaries , Plan International Sudan’s Strengthening food production and access to food resources through renewable energy solutions for vulnerable populations living in host communities and refugee camps in Sudan.**

**Organization Background**

Plan International is an independent child rights and humanitarian organization committed to children living a life free of poverty, violence and injustice. We actively unite children, communities and other people who share our mission to make positive lasting changes in children’s and young people’s lives. We support children to gain the skills, knowledge and confidence they need to claim their rights to a fulfilling life, today and in the future. We place a specific focus on girls and women, who are most often left behind. We have been building powerful partnerships for children for more than 75 years, and are now active in more than 70 countries. In Sudan Plan operating in four states which are White Nile, North Kordofan, Kassalla and North Darfur. The assessment to be conducted White Nile South Sudanese Refugees camps and host communities in AL Salam locality with more focus on Al Redis 1 and Redis 2 hosting communities, Al Redis1 and Al Redis2 camps.

1. **Project Background:**

The current crisis in South Sudan (SSD) started in Dec. 2013 and affects the South Sudanese population. The project focus on refugees displaced to White Nile state in Sudan particularly refugees in Al Redis1 and Al Redis 2 and the host communities.

The project intends to create employment and self-employment opportunities for the refugees affected by the Conflict in South Sudan and other nearby countries, by providing with capacity building trainings and the development of Income Generating Activities based on renewable Energy solutions such as a Multifunctional Platform, a solar oven and IGAs connected with MSP or any other practical options that in line with the current situation on the ground determined by the assessment performed by an Independent Consultant, which will be installed by the project.

The project is designed around three Expected Results - each representing a thematic component, which complements the following:

* Component 1: The women and young beneficiaries acquired the technical, financial and management skills needed to manage and maintain the renewable energy systems for food production, namely the multifunctional solar platform and the community solar oven.
* Component 2: Strengthening food security for women and youth through the development of renewable energy-based food production/distribution in the refugee camp and host communities.
* Component 3: The set-up of Renewable Energy IGAs are supported and accompanied by providing more economic resources to vulnerable households to ensure greater food security.

**Project Objective:** Strengthening food production and access to food resources through renewable energy solutions for vulnerable populations living in host communities and refugee camps in Sudan

* Outcome 1: Strengthening the technical and management capacities of the local host community and refugees for renewable energy systems related to food production and distribution.
* Outcome 2: Improving access to food through renewable energy systems for women and youth in refugee camps and host communities.
* Outcome 3: Strengthening the purchasing power (of food) of the refugee and host communities through income-generating activities based on renewable energies.

Beneficiaries (Please see Annex 2 for more information).

1. **Labor Market Assessment Purpose and scope**

The main purpose of the study is to provide a comprehensive labor market assessment covering economic sectors in Elsalam and Egabalin localities in White Nile State including refugees setting and the towns namely Alsalam and Elgabalin, focusing on businesses and vocations that are in high demand including employers and businesses needs and potential labour requirements for youth from refugees and host communities. This labour market scan shall clearly look at and identify both sides (demand and supply).

Additionally, the assessment is expected to provide the project with the analysis of the target population and provision of the list of people who show interest in participating from the project in the different modalities which are:

1. Benefit from the Training of Trainers in both technical and business training, and replicate the acquired knowledge in a further training with the rest of the beneficiaries. There will be 10 trainees.
2. Benefit from the trainings delivered by the trainees from the ToT in technical and business knowledge, including the elaboration of a business plan and the possibility to develop an Income Generating Activity in the projects frame.
3. Participation from the Management Committee of the Multifunctional Platform and the Solar oven or any other equipment selected and agreed upon to be following the Independent Consultant’s assessment that will be installed by the project.

The market & energy need assessment is meant to focus on the following main components:

Market dynamics, business structures and business demand by:

* identifying opportunities of both waged and self-employment in refugees and host community settings. The Study will look for information regarding existing IGAs as well as current and Future needs for trained persons and trades/businesses that are in high demand.
* Identifying the employment needs of businesses and business viability within refugee camps markets, host communities’ markets, analysis of purchasing power as well as potential linkages with business owners and mentors.
* Identifying labor market needs in terms of skills gaps and market demands to inform interventions for vulnerable adolescent / Youth girls & boys to determine market opportunities, mapping and assessment of existing IGAs and potential income generated activities (IGA), considering specifically girls and young women meaningful inclusion and participation.

Social characteristics, dynamics and gender analysis

* Conduct gender and power relations analysis in both refugees and hosting communities context.
* Analyze population characteristics and facilitate a proper gender responsive and need-based selection of beneficiaries.

Energy needs assessment:

* Assess the current energy and power supply in the refugees camp and host communities and engaging relevant actors as well as barriers facing power generated IGAs.
* Assess the viability of alternative safe power supply system (Solar generated).
* Map out specification of power need and capacity requirements.
* Assess the security and safety situation with regards to energy foundation set-up.

The findings should be able to provide information on/ identify:

* market needs and current livelihood options including viable businesses for potential business creation and entrepreneurial skills development as well as existing businesses.
* Current context on women’s situation regarding employment and self employment.
* challenges, barriers, limitations and specific consideration related to gender.
* specific skills/capabilities and linkage with employment opportunities.
* Issues affecting current small and medium size businesses in camps and hosting communities .
* training and activities needed for refugees / host communities
* Identification of value chains where to insert small businesses.
* Mapping of Micro finance institutions which can potentially finance IGA not covered by the project.
* Characterization of local community members in terms of payment capacity and basic needs, which will be fundamental for the definition of the tariff scheme for the services provided by the renewable energy systems installed as well as for the IGAs business plan design.
* Recommendations.

Additionally, the assessment is expected to perform the selection of the beneficiary who will be part of the Project. As a result from the assessment, the candidates for the 10 members TOT will be selected, as well as for the 40 potential Income Generating Activities (IGAs) developers (20 for El Redais 1 camp & hosting community and 20 for El Redais 2 camps & hosting community), the10 members of the two management committees of the solar Oven ( five members for El redais1 and El redais2 refugees and hosting communities) and the10 members of the two management committees of the MSP ( five members for El redais1 and El redais2 refugees and hosting communities) (Please see Annex 2.Project proposal) based on the following criteria:

1. Capacity to be part of the ToT and replicate the training to the rest of the beneficiaries.
2. Willingness to participate and develop an IGA.
3. Leadership and management skills.
4. At least 60% of them will be women.
5. **Plan International Sudan Responsibilities:**

* Arrange and manage approval of assessment from government and conduct community mobilization coordination with local partners and CBOs, recruit the enumerators.
* Provide the assessment team all the relevant project information.
* Project Manager & YEE lead, MEAL Coordinator, ITNO and SPNO will be involved in all assessment process to ensure that this exercise meets the project objective.
* Ensure the dissemination of the study report.

1. **Consultant Activities and Responsibilities:**

The consultant will provide a detailed proposal of assessment methodologies to address youth needs and to ensure identified project beneficiaries through Best Interest Assessment (BIA) (see Annex 3) participated in this assessment and targeted by interviews in order to the know vocational and entrepreneurship training needs for this out-of-school.

The key activities will include but not be limited to the following:

* Desktop review and analysis of the relevant secondary data/information
* Provide Plan International with a specific work plan and data collection tools such as surveys.
* Collect and update Primary data through diversified interviews and focus groups including specific groups for women (include female interviewers)
* Conduct or update the 3 components of this assessment listed above (Market dynamics, business structures and business demand, Social characteristics, dynamics and gender analysis, Energy needs assessment) in a participatory manner.
* Analyses data and connect results. Submission of a draft report and finalize it based on comments and inputs from Plan International.
* Conduction of assessments findings dissemination and results validation workshop.
* Submission of assessment report and presentation dually to Plan International, ITNO to reflect that Italian government focal point.

1. **Expected Consultant Deliverables**

* Submit technical narrative and financial proposal, including a proposed methodology for the study.
* Specific workplan and data collection tools.
* Data collection (secondary data and primary data) and analysis for market assessment
* Submit draft market assessment report
* Consolidate comments and improve the draft market assessment
* Submit Final Report in English, including:

1. Main results from the Assessment attending all expected data described in section 3 of the present ToRs.
2. Full list of institutional and individual contacts developed throughout the market assessment as well as compiled raw data from market research and interviews in electronic format using use Plan International guide. (Report structure see Annex 1)
3. List of beneficiaries identified from the project including: name, age, gender, contact information, comments, specific activity they can participate from (ToT, Trainings, management committees)
4. **Consolidative with deliveries**

The study is expected to be started on the 25 th of August 2024 as below timeline:

**Week 1:**

- Induction with Plan Staff (safeguarding…. 1 day

- Provision of data collection tools by the consultant for further review.

- Definition and sharing of the materials needed for the desk review

**Week1:**

* Delivery of the workplan
* Assessment tools refined as needed
* Desk research and key stakeholder interviews

**Week2-3 :**

* Collection primary labor market actors, training providers, potential partners and business/trade associations (continue)
* Data consolidation, analysis and report writing
* Share draft report with Plan
* Presentation of key findings to Plan International staff and key stakeholders at White Nile and results validation meeting.

Week 4:

* Consolidation of report with outcomes of the meeting by the consultant
* Share final report

1. **Consultant Profile**

* At least 5 years of experience in consulting and labor market research and renewable energy based IGAs (to be demonstrated with similar jobs performed in the past).
* Familiarity with White Nile State especially refugees business community
* Well-connected to Business and Trade Associations and other industry platforms.
* Excellent labor market research and networking skills
* Excellent knowledge of gender equality and protection issues
* Excellent communication skills.
* Knowledge of statistics and experience using KOBO tool.
* Gender balanced team

1. **Submission Information:**

Interested candidates are invited to submit via email one (1) application package to Operation Support Service Department via Mohamed.Abdelgadier@plan-international.org and [Ahmed.Ibrahim@plan-international.org](mailto:Ahmed.Ibrahim@plan-international.org) before the September 10, 2024.

* CV in English which clearly states relevant expertise/experiences;
* 1 technical proposal including detailed work-plan and methodology, including but not limited to:
  + Sampling method
  + Techniques and tools used to collect, prepare and analyze information and data, including software used.
* 1 financial proposal.

Only shortlisted candidates will be contacted for further steps.

1. **Estimated Duration (up to 4 weeks)**
2. **Data Confidentiality and Privacy and Safeguarding of children and young people**

The Consultant undertake to respect and protect the confidentiality of all information acquired as a result of or pursuant to this Term of Reference and will not, without the other Plan International prior written consent, disclose any such information to a third party, unless it is required to do so by any applicable law or regulation or is specifically authorized, Plan International must comply with Applicable Law and implement any additional policies or procedures as required[[1]](#footnote-1). Moreover, other Plan International policies impose additional requirements regarding the collection, use, and protection of particular classes of Personal Data, including the requirements described in the Global Policy Safeguarding Children and Young People[[2]](#footnote-2).

The Consultant must read, sign on and apply Global Policy Safeguarding Children and Young People in all the process of this study.

**Terms of Payment**

Plan international Sudan shall pay the consultancy fee to the consultant as agreed between both the parties by contract agreement in SDG.

p. All expenses shall also be included in the contract agreement. Initial payment of 30% will be made upon the signature of this agreement with detailed work plan approved by Plan international- Sudan and the Bank, the remain being paid upon the delivery of the completion of all previously outlined activities.

1. **Annexes**
2. **Report structure Market Scan Assessment (including desk review)**

Table of Contents

CONSULTING

TEAM ACKNOWLEDGEMENTS

List of tables

Acronyms

EXECUTIVE SUMMARY

**1. Purpose, goals and use of the study**

1.1. Rationale for the study

1.2. Purpose of the study

1.3. Objectives of the study

1.4. Scope of the study

1.5. Use of findings

**2. Methodology**

2.1. Overall Approach to the study

2.2. Sampling and sampling procedures

2.3. Data collection Methods

2.4. Data collection procedures and processes

2.5. Ethical Considerations

2.6. Quality control

2.7. Limitations

**3. Baseline situation and analysis of the problem (desk review)**

3.1. Introduction

3.2. Socio-Economic, political and cultural country contexts

3.3. Relevant policies, legal frameworks and national labor legislation for youth employability, especially regarding refugees

3.4. Problem Analysis based on Country Context

3.5. Description of analyzed economic and energy sectors and growth trends in the country context

3.6. Situation of youth and women with focus on their participation in the labor market, working conditions, working environment and specific vulnerabilities for joining the labor market

3.7. Overview of existing programs in the field of youth economic opportunities

**4. Analysis of the different economic and energy sectors/ market assessment**

4.1. Growth trends of the sectors

4.2. Gender sensitive analysis of barriers and opportunities for youth in the identified sectors (including specific section on women)

4.3. Analysis of the underlying causes of youth and women unemployment and employability in the identified sectors

4.4 Identification of potential feasible Income Generating Activities according to market demands.

4.5 Identification of the beneficiaries for the project.

**5. Analysis of relevant stakeholders and target group**

5.1. Target Group Analysis

5.1.1. Socio-Economic Target group analysis

5.2. Stakeholder Analysis

5.2.1. Analysis of State Actors strategies, interventions and gaps

5.2.2. Private Sector Actors

5.2.2.1. Relevant businesses and companies in the identified sector

5.2.2.2. Analysis of the interest of business and companies in a cooperation

5.2.2.3. Needs assessment of the Private Sector Actors in terms of access to qualified labor force

5.2.2.4. Qualified estimation of number and quality of internships and practical training which can be conducted in cooperation with the Private Sector

5.2.5. Relevant Actors in the field of development (non-governmental institutions) and respective programs

5.2.6. Relevant locally registered non-profit organizations in the field of development (non-governmental institutions) with proven expertise in the implementation of youth economic empowerment.

5.2.7 Relevant value chains in which the IGAs can be inserted.

5.2.8 Present Micro Finance Institutions which could finance IGAs.

6.1 Recommendations of the economic sector(s) for the project intervention and project measures

6. 2 Other recommendations and conclusions

1. **Project Proposal**
2. **Project Log frame work**
3. **Plan Child Protection Policy**
4. **Best Interest Assessment (BIA)**

1. Data Privacy Policy, Plan International, March 2018. [↑](#footnote-ref-1)
2. Global Policy Safeguarding Children and Young People, Plan International, November 2017. [↑](#footnote-ref-2)