## Sheet1
Preamble: The team consultant will work with a team of other two collegues to ensure quality of work. The work will be done in 30 days including weekends. The lead will be paid 250USD daily, the Technical review will be paid 150USD per day, and the Nvivo Analyst will be paid 161USD per day. this therefore means a daily rate of 561USD per day.
No | Key activity | Days | Rate | Total
1 | Pre-reads about CHWs | 2 | 561 | 1122
2 | Pre-reads about GESI | 2 | 561 | 1122
3 | Development of the inception report | 2 | 561 | 1122
4 | Development of the Storyline for the CHW-AIM paper | 5 | 561 | 2805
5 | Facilitate back and forth on the storyline and its approval | 2 | 561 | 1122
6 | Kick start of consolidation of Key data sets from the 3 states | 3 | 561 | 1683
7 | Populating the Storyline with key information | 2 | 561 | 1122
8 | Re-Analysis and combination of KIIs and FGD in Nvivo | 2 | 561 | 1122
9 | Search for the Journal, submit for approval to publish | 1 | 561 | 561
10 | Submission of the Final draft paper to the team for review | 1 | 561 | 561
11 | Editing the comments coming from WV team | 3 | 561 | 1683
12 | Submission of the paper to the prefered journal | 2 | 561 | 1122
13 | Peer Review Support | 3 | 561 | 1683
|  | 30 |  | 16830