TERMS OF REFERENCE (ToR)

Consultancy: Adaptation of HEA Outcome Analysis for Anticipatory Action

GFFO-funded project “Reducing the Impact of Predictable Shocks by Initiating Community-Based Anticipatory Action in Sudan (2024–2026)”.

- Background

Save the Children Sudan is implementing Anticipatory Action (AA) programming under the GFFO-funded project “Reducing the Impact of Predictable Shocks by Initiating Community-Based Anticipatory Action in Sudan a (2024–2026)”.

As part of this work, a Household Economy Approach (HEA) baseline and Outcome Analysis (OA) has been completed across five livelihood zones, providing critical insights into household vulnerability, food security gaps, and livelihood dynamics. While the OA offers a strong analytical foundation, it is currently not fully operational for anticipatory action, SC would like to further develop:

- Hazard-specific scenario analysis (flood & drought)

- Clear linkage to trigger thresholds and lead times

- Direct usability for activation decisions and early action planning

This adaptation is critical to bridge the gap between analysis and action. While the HEA Outcome Analysis already identifies who is vulnerable and why, Anticipatory Action requires translating this evidence into when to act, where to act, and how to act before impacts fully materialize. Therefore, SCI now seeks to adapt this analysis into a decision-oriented AA analytical product, aligned with operational needs in Blue Nile and Red Sea States.

- Purpose of the Assignment

The purpose of this consultancy is to transform the existing HEA Outcome Analysis into an Anticipatory Action–oriented analytical tool, enabling:

- Trigger-based decision-making

- Hazard-specific scenario planning (flood & drought and human epidemics)

- Operational use for EAPs, trigger matrices, and early action design

- Strategic use for advocacy and influencing

These outputs will enable SCI Sudan to move from analytical understanding of vulnerability to trigger-based operational decision-making, ensuring that early action is timely, targeted, and aligned with forecast information and community-level risks.

- Objectives

The consultancy aims to adapt the existing OA to reflect hazard-specific AA scenarios for flood and drought in BN and RS; translate OA findings into trigger-relevant indicators and thresholds; integrate scientific lead-times and seasonal timelines into the analysis; strengthen the link between HEA analysis and AA activation decision-making

Outputs usable for:

- EAP refinement

- Trigger matrices

- AA activation protocols

- Advocacy and influencing

This will ensure that HEA is not only used for post-shock analysis but becomes an integral component of early warning systems and anticipatory activation protocols, supporting decisions before households' exhaust coping mechanisms.

- Scope of Work

The consultant will undertake the following:

4.1 Platform Customization for Sudan Context:

Review:

- Existing HEA baseline and OA report

- AA guidance materials (provided by SCI)

- Existing EAPs (BN & RS – where relevant)

Identify key gaps in relation to:

- Hazard specificity

- Trigger linkage

- Operational usability for AA

This step will ensure that the consultancy clearly identifies the gap between the current analytical outputs and the operational requirements of Anticipatory Action, particularly in terms of trigger usability, hazard specificity, and decision-making relevance.

4.2 Development of Hazard-Specific Scenarios

Develop AA-oriented outcome scenarios for:

- Flood senarios (Blue Nile & Red Sea)

- Drought senarios (Blue Nile & Red Sea)

Each scenario should include:

- Expected household-level impacts

- Timing and evolution of shocks

- Differences across wealth groups

- Implications for children and vulnerable groups

Scenario development will translate generic outcome analysis into shock-specific impact projections, enabling SCI to anticipate how floods and drought will affect households differently across locations and wealth groups.

4.3 Trigger-Relevant Indicator Framework

From the OA, identify and structure key indicators for AA triggers, including:

- Food consumption gaps

- Livelihood coping strategies

- Market access and price changes

- Water availability and livestock stress

- Nutrition-related indicators

Translate these into:

- Operational trigger thresholds

- Early warning signals aligned with forecasts (SMA/ICPAC)

- Lead-time relevance (weeks/months before impact)

This component is critical to convert analytical indicators into operational trigger systems, ensuring that monitoring data (e.g., prices, rainfall, NDVI) can directly inform activation decisions rather than remain descriptive.

4.4 Integration with Lead-Time & Forecasting

Align OA findings with:

- Seasonal calendars

- Forecast windows

- Scientific lead-times

Define:

- When action should be taken (activation window)

- What indicators should be monitored at each stage

Integrating lead-time ensures that early actions are implemented within the anticipatory window, allowing interventions to take place before peak impact, rather than as a response after crisis onset.

4.5 Operationalization for Anticipatory Action

Translate analysis into practical outputs for field use, including:

Linkage between:

- Trigger → Impact → Early Action

Recommendations for:

- Targeting (which groups, when)

- Type of early actions

- Geographic prioritization

Alignment with:

- EAPs

- Trigger matrices

- AA SOPs

This step ensures that the analysis is translated into practical programming decisions, including who to target, what assistance to provide, and when to act, aligned with EAPs and SOPs.

4.6 Advocacy and Strategic Use

Produce a concise analytical brief (aligned with your example) and serves as evidence for AA investment, highlighting:

- Key risks

- Anticipated impacts

- Urgency of early action

The analytical brief will translate technical findings into clear, decision-oriented messaging, supporting donor engagement, resource mobilization, and positioning of Anticipatory Action as a cost-effective response approach.

  - Validation

Facilitate validation sessions with SCI teams and relevant stakeholders – one session in BN and one session in RS. Validation sessions will ensure that outputs are contextually grounded, technically sound, and operationally feasible, incorporating feedback from programme teams and stakeholders.

- Deliverables

The consultant will deliver:

5. 1. Inception Report

- Methodology

- Workplan

- Adaptation framework

5.2. AA-Oriented Outcome Analysis Report (Main Deliverable)

Revised OA including:

- Flood & drought scenarios (BN & RS)

- Trigger-relevant indicators

- Lead-time integration

- Decision-use framework

This report will serve as the core analytical backbone for AA decision-making, linking hazard scenarios, projected impacts, and triggering thresholds into a single, operational framework.

5.3. Trigger & Indicator Summary Table

Clear mapping: Indicator - Threshold - Lead time - Decision use

This table will provide a clear and actionable reference for monitoring and activation, ensuring consistency between analysis, early warning systems, and decision-making processes.

5.4. Operational Summary (for Program Teams)

- Short, practical guidance

- Direct link to EAP use

Designed for programme teams, this output will simplify complex analysis into practical guidance, enabling field teams to integrate findings into EAP implementation and activation protocols.

  - Advocacy / Strategic Brief

Based on OA findings - Clear, concise, stakeholders-ready. This brief will support evidence-based advocacy, demonstrate the value of early action, and highlight the risks of delayed response.

Desirable Timeline Deliverables

| # | Deliverable | Description | Timeline |
| --- | --- | --- | --- |
| 1 | Inception Report | Methodology, workplan, timeline | Week 1 |
| 2 | Adapted OA Report (AA-focused) | Scenario-based OA with triggers and lead-times | Week 4 |
| 3 | AA Dashboards | Visual decision-support tools | Week 5 |
| 4 | Analytical Briefs | 2 short AA briefs (one of each flood/drought) | Week 5 |
| 5 | EAP Integration Guidance | Practical recommendations for use in EAPs | Week 5 |
| 6 | Technical Session - Validation | 2 sessions with SCI team & stakeholders | Week 6 |
| 7 | Final Report | Consolidated deliverables | Week 6 |

6. Duration

Estimated duration: 20–25 working days

7. Required Qualifications

- Strong expertise in HEA and Outcome Analysis

- Demonstrated experience in Anticipatory Action / Forecast-based Financing

- Experience working in complex humanitarian contexts (Sudan preferred)

- Strong analytical and writing skills

8. Reporting

The consultant will report to: AA Project Lead / MEAL Manager – SCI Sudan

9. Location

Remote, with regular engagement with SCI Sudan team. Ideally, but not mandatory validation sessions in person.

10. Annex: Predicting the impacts of El Nino for Anticipatory Action_findings from a HEA assessment - This is an example that can be shared when advertising the consultancy. To exemplify what SC is expecting from the consultancy. Predicting the impacts of El Nino for Anticipatory Action_findings from a HEA assessment | Save the Children’s Resource Centre.

11. Added Value of the Consultancy (NEW SECTION)

This consultancy will enable SCI Sudan to transition from a strong analytical foundation to a fully operational Anticipatory Action system, where evidence directly informs trigger-based activation.

By integrating HEA Outcome Analysis into early warning and decision-making processes, SCI will strengthen its ability to:

- Act earlier and more effectively

- Target the most vulnerable populations

- Reduce humanitarian impact and costs

This approach aligns with global best practices in AA, where HEA serves as the evidence backbone for impact-based triggering and early action design