Terms of Reference

Final Evaluation:  EU inclusive quality education for the most vulnerable children in Sudan

March 2026

# Table of Contents

Table of Contents	1

1.	Project Summary	2

2.	Introduction	3

3.	Background and Context	3

4.	Scope of Study	6

4.1	Purpose, Objectives and Scope	6

4.2	Intended Audience and Use of the Study	6

4.3	Key Study Questions	7

5.	Study Methodology	10

5.1 Study Design	10

5.3	Data Sources and Data Collection Methods / Tools	12

5.4	Ethical Considerations	13

6.	Expected Deliverables	14

7.	FINAL EVALUATION Management	15

8.	Study Team and Selection Criteria	17

9.	Schedule of Payment	19

10.	HOW TO APPLY	19

11.	Annexes	19

# Project Summary

| Type of study | Final Evaluation |
| --- | --- |
| Name of the project | EU inclusive quality education for the most vulnerable children in Sudan (NDICI AFRICA/2022/439-484) |
| Project Start and End dates | Start date: 01 January 2023 End date: June 30 2026 |
| Project duration | 42 months (3 years 6 months) |
| Project locations: | Republic of Sudan: North Kordofan, South Kordofan, Blue Nile, Sennar, Red Sea, River Nile and Khartoum States |
| Thematic areas | Basic education, child protection and child rights governance |
| Donor | The European Union (INTPA) |
| Estimated beneficiaries | 78,000 children (40,802 girls and 37,198 boys) |
| Project stakeholders | State Ministry of Education Ministry of Social Affairs Ministry of Finance National Council of Child Welfare (NCCW) State Council of Child Welfare (SCCW) Primary schools, ALPs and catch-up classes Parent-Teacher Associations, Mothers Groups, Community-Based Child Protection Networks (CBCPNs), Community level Transparency and Accountability structures Community leaders Case workers |
| Overall objective of the project | Contribute to ensuring that girls and boys in Sudan realize their right to quality, safe and inclusive primary education in a protective environment. |

# Introduction

The project “Inclusive Quality Education for the Most Vulnerable Children in Sudan”, funded by The European Union (INTPA), aims to support education and child protection services in seven states in Sudan: North Kordofan, South Kordofan, Blue Nile, Sennar, River Nile, Red Sea and Khartoum. The project started in January 2023 and will end in June 2026.

The project seeks to ensure that girls and boys in Sudan realize their right to quality, safe, and inclusive primary education within a protective environment. Its specific objective is to create a safer, enabling learning environment for vulnerable children, including girls, boys, children with disabilities, refugees, internally displaced children (IDPs), and other out-of-school children.

In response to the significant challenges facing Sudan’s education sector and in alignment with the Education Sector Strategic Plan, the project identified four strategic priorities: improving access to education, increasing the availability of nutritious food, strengthening child protection services, and enhancing investment in children’s rights. These priorities were reflected in four interconnected outcomes: improving access to education, increasing the availability of nutritious food, strengthening child protection services, and promoting the realization of children’s rights.

These terms of reference (ToR) outline the requirements for the final evaluation of the project. Save the Children will conduct a final evaluation between the period of March to August 2026. The overall objective of the final evaluation is to systematically and objectively assess the project's performance, outcomes and impact, in line with OECD DAC evaluation criteria, to inform decision-making, accountability to the donor and stakeholders, support organizational learning, and provide learning and strategic recommendations for future programming and improvements in the education sector. The evaluation will also compare endline results with baseline findings.

# Background and Context

Since the inception of the project, Sudan has faced a highly challenging context characterised by political instability, conflict, economic hardship, and social distress, further exacerbated by the COVID-19 pandemic, floods, and disease outbreaks. Political unrest and recurrent teachers’ strikes due to low wages have also created a difficult environment for the implementation of education programmes.

The outbreak of conflict in April 2023 between the Sudanese Armed Forces (SAF) and the Rapid Support Forces (RSF) has severely disrupted the education system. In several project locations, schools and education services have remained closed for more than two years. As the conflict expanded to multiple regions, including central states and the Kordofan region, access to project areas became increasingly constrained. Essential services have been disrupted in 12 of Sudan’s 18 states, including Khartoum, Kordofan, Darfur, and Gazira.

The conflict has led to mass displacement, making Sudan the country with the highest number of internally displaced persons globally, including approximately 5.5 million school-age children. Access to food, water, shelter, and basic services has been deeply compromised. Education has been particularly affected, with widespread school closures, damage to infrastructure, and the use of schools as emergency shelters for displaced populations. As a result, more than 6 million children dropped out of school.

Beyond the immediate impacts of the conflict, Sudan’s education sector has continued to face significant structural challenges. Displacement, insecurity, and economic hardship have increased the number of out-of-school children and exacerbated pre-existing issues such as poverty, harmful social practices, and inadequate educational infrastructure. Child marriage and child labour remain widespread, while children face heightened risks of recruitment into armed groups and exposure to violence and exploitation. Additional barriers to education include long distances to schools, limited transportation, inadequate infrastructure, and insufficient support for children with disabilities.

Food insecurity further undermines children’s access to education and learning outcomes. Rising food prices and the suspension of school feeding support by the World Food Programme (WFP) have left many students without access to regular meals. Only a limited number of schools currently provide school feeding programmes, and shortages of clean water further constrain their implementation.

The ongoing conflict between RSF and SAF has significantly affected the project, including access to project locations, particularly in active conflict regions. The project was initially designed to support 160 schools across South Kordofan, the Red Sea, Khartoum, Central Darfur, North Darfur, and North Kordofan states.

Following the escalation of conflict in Darfur and Khartoum, project activities were relocated to more accessible and secure areas. Implementation therefore focused on South Kordofan, North Kordofan, and Sennar, while activities initially planned for North Darfur and Khartoum were relocated to the Red Sea, River Nile, and Blue Nile states.  During the final six months of the project, improved access to Khartoum State enabled a partial return of activities to the capital. Interventions have since focused on rehabilitating school infrastructure in conflict-affected areas, particularly in Sharg Alneel and Karari localities.

The project aimed to ensure that children in Sudan, especially girls, boys, children with disabilities, and internally displaced children (IDPs), have access to safe, inclusive, and quality primary education within a protective environment. It was built around four core areas: expanding access to education, improving child nutrition, strengthening protection services, and promoting children’s rights.

The project addressed infrastructure gaps, promoted inclusive and child-centered teaching approaches, and strengthened education quality assurance systems. It supported the provision of daily nutritious meals in targeted schools and raised community awareness of appropriate feeding and nutrition practices to enhance children’s wellbeing and school attendance. Preventive and responsive child protection services were reinforced, including the provision of case management support to children at risk of violence or other rights violations, alongside strengthening community-based mechanisms to reduce violence, abuse, neglect, and exploitation. The project also amplified children’s voices and enhanced transparency and accountability in service delivery through child consultations and child-led media initiatives. Additionally, the intervention sought to strengthen stakeholder capacity to respond to both immediate and long-term needs of vulnerable children, contributing to improved protection, participation, and learning outcomes.

Final Beneficiaries

The project targeted a total of 78,000 children (40,802 girls and 37,198 boys), prioritizing the most vulnerable and marginalized groups. Approximately 30% of the targeted children were internally displaced (IDPs), reflecting significant population movements in the targeted states following the conflict. The target group included 600 children with disabilities (CwD) and 600 unaccompanied and separated children, as well as children at risk or survivors of violence. These children were expected to benefit from formal primary education, Accelerated Learning Programme (ALP) centres, and non-formal education activities, including transitional pathways to facilitate(re)integration into formal schooling.

- 67,667 children (32,270 boys and 35,397 girls), including IDPs in Sennar, Red Sea, North Kordofan, and South Kordofan states, were targeted to receive nutritious meals. The school feeding component was designed to reach schools not supported by WFP, as well as non-formal education settings serving street-connected, working, and out-of-school children.

- The project also targeted 5,099 teachers and school staff (2,845 female and 2,254 male), including PTAs and Mothers’ Group members. In response to overcrowded classrooms, limited incentives, lack of salaries, and weakened institutional capacity due to displacement of qualified personnel, professional development opportunities were provided as well as infrastructure rehabilitation, and targeted capacity-building initiatives, including tailored support for Mothers’ Groups.

- Furthermore, 160 Parent–Teacher Association (PTA) and Mothers' Groups (MG) committees across 160 targeted schools were sought to engage and strengthen. These structures were intended to play a critical role in promoting community participation, supporting school governance, and enhancing accountability in service delivery. Capacity-building efforts were designed to equip PTA members with the knowledge and skills required to contribute to school improvement planning, monitor attendance and retention, support inclusive education practices, and promote child protection within school environments. By reinforcing the role of PTAs, the project aimed to strengthen school–community linkages, increase local ownership of education initiatives, and contribute to the sustainability of education and protection outcomes beyond the project period.

- The project aimed to strengthen 26 Community-Based Child Protection Networks (CBCPNs), comprising 390 members, in order to address gaps in local child protection mechanisms and improve referral and response pathways for vulnerable children. In parallel, the project targeted 8,000 parents and caregivers across six states with positive parenting sessions designed to promote safe, supportive, and protective home environments for children.

- The project also aimed to mobilise and support 540 child rights champions (270 girls and 270 boys) from 160 child rights clubs to participate in advocacy and public awareness initiatives targeting government stakeholders. Through these activities, the project sought to reach approximately 12,000 community members with key messages on child rights, education, and protection.

- In addition, the project was designed to work closely with duty-bearers to strengthen institutional commitment to child rights, including the promotion of inclusive education and the prevention of child labour, abuse, and school dropout.

# Scope of Study

## Purpose, Objectives and Scope

The primary purpose and objective of the final evaluation is to systematically and objectively assess the project's performance, outcomes and impact, in line with OECD DAC evaluation criteria, to inform decision-making, accountability to the donor and stakeholders, support organizational learning, and provide learning and strategic recommendations for future programming and improvements in the education sector. The evaluation will also compare endline results with baseline findings.

Scope of the Final Evaluation

The final evaluation will assess the project's overall performance, results, and contributions across the entire implementation period, from January 2023 to June 2026. The evaluation will examine the extent to which the project has achieved its intended results, including outcomes and impact, in line with the OECD DAC evaluation criteria, including relevance, coherence, effectiveness, efficiency, impact, and sustainability, while also assessing cross-cutting priorities such as child rights, inclusion, gender sensitivity, accountability to affected populations, and child participation.

Geographically, the evaluation will cover seven states in Sudan where the project has been implemented: North Kordofan, South Kordofan, Blue Nile, Sennar, Red Sea, River Nile, and Khartoum. Within these states, the evaluation will focus on selected project-supported interventions and although Khartoum State is within the project's geographic scope, its coverage in the final evaluation will be limited as the project has been implemented for a rather limited time period in Khartoum, as this state was reintegrated only during the final months of the project and was therefore also not included in the baseline study.

## Intended Audience and Use of the Study

Primary intended audience of the study are listed in the table below

| Primary Audience | Further information |
| --- | --- |
| Project donor | The European Union (INTPA) |
| Primary implementing organisation | Save the Children International, Sudan CO |
| Project partners | Save the Children Finland, World Vision United Kingdom, World Vision International, Journalists for Children, SABAH Association for Child and Family Care and Development, Child Development Foundation, Sudanese Organization for Relief & Recovery |
| Government stakeholders | State Ministry of Education Education Unit at locality level Ministry of Social Affairs Ministry of Finance National Council of Child Welfare (NCCW) State Council of Child Welfare (SCCW) |
| Community groups/institutions | Primary Schools, ALPs, Catch up class, MGs, CBCPNs; Parent-Teacher Associations; Community leaders; Case workers in North Kordofan, South Kordofan, Blue Nile, Sennar, Red Sea, River Nile, Khartoum |
| Beneficiaries | Children and Adults involved in the project |
| International development/humanitarian research community | Education Cluster Regional Teachers Initiative for Africa Local Education Group Child Protection Cluster |

The findings of the Final Evaluation will be used by project decision-makers to inform adaptive programming, strengthen accountability, guide future improvements in education service delivery, child protection services, child participation practices and access to essential services in Sudan, and support justification for the expansion or scale-up of the programme. In addition, programme staff will disseminate and discuss the Final Evaluation findings during a project learning event with relevant stakeholders.

## Key Study Questions

The table below includes criteria listed the key study questions those are generic questions that apply to different types of evaluations – to cover these questions is dependent on time and budget.

| Criteria | Key Study Questions | Process | Outcome | Impact |
| --- | --- | --- | --- | --- |
| Accountability | - How has the project approached accountability to children and the wider community? | X | X | X |
| Child participation | - How have the children, their needs, desires and suggested solutions, been consulted and accounted for in project design and implementation? - How were children supported to meaningfully participate across the project cycle? | X | X | X |
| Child rights programming | - How has the project design and implementation considered a child rights approach? | X | X |  |
| Safe programming | - Has the project been designed, planned, implemented and monitored to ensure it is safe for children and adults? - How has child safety been integrated into the project design and implementation of activities? What aspects of the project make children feel safe? - How has the project assessed the risks for children and do these risks still exist to date? Have they been reduced, controlled and managed by the minimising actions? | X | X |  |
| Coherence* | - Does the intervention support beneficial synergies and linkages with other interventions carried out by Save the Children in the country/community? - Is the intervention consistent with the interventions of other actors in the same context, such as supporting complementarity, harmonization, and co-ordination with government and other relevant service providers? |  |  |  |
| Effectiveness* | - Did the project achieve its intended outcomes? - Are there any differences in outcomes achieved by different groups? - Were there any unintended outcomes? - Are the objectives of the project being achieved? - How big is the effectiveness or impact of the project compared to the objectives planned? |  | X | X |
| Efficiency* | - Were objectives achieved on time? (and budget) - Were activities cost-efficient? (What was the cost of delivering outputs? How were cost drivers managed?) - Was the project implemented in the most efficient way compared to alternatives? | X | X |  |
| Equity and equality | - Did the intervention have an impact on inequality or marginalization? - Is there evidence that the intervention reduced inequality and marginalization for specific groups? - What mechanisms/factors contributed to this result? |  | X | X |
| Impact* | - Does the project contribute to reaching higher level objectives (preferably, overall objective)? Why/ why not? - What is the impact or effect of the project in proportion to the overall situation of the target group or those effected? - What are the intended or unintended effects of the project, either positive or negative, direct or indirect? |  |  | X |
| Inclusion | - How did the project consider inclusion of vulnerable groups in the design and its implementation of activities? | X | X | X |
| Process | - How well did staff/partnerships work together? - How good was the coordination when implementing the project? - Have MEAL activities been implemented as planned? Were they relevant and appropriate? How could they be improved? | X | X |  |
| Relevance* | - Are we doing the right thing? Does the intervention respond to clearly identified needs and priorities of the project participants? Was the intervention appropriately adapted to the local context and target population? - How was learning and evidence was used throughout the project cycle to adapt and ensure the project remained relevant? - How important is the relevance or significance of the intervention regarding local and national requirements and priorities? - Are the activities and outputs of the project consistent with the intended impacts and effects? | X | X | X |
| Sustainability* | - Are the positive effects or impacts sustainable? - How are the sustainability or permanence of the intervention and its effects to be assessed? |  | X | X |
| Gender sensitivity | - How has the project considered gender sensitivity both in the design and its implementation of activities? - Has the project incorporated different needs and accessibility of boys and girls, men and women, and non-binary individuals? - Has the project outcomes or results been equally represented? - What are the gender gaps that the project addressed and what remaining aspects need to be considered further? | X | X | X |

# Study Methodology

## 5.1 Study Design

The study will use a mixed-methods approach (quantitative and qualitative methods) to enhance reliability of the findings (triangulation). It will consist of review of documents from SCI and other sources related to humanitarian and development work, particularly clusters reports and reports from other organizations. Quantitative surveys will collect data to compute relevant indicators on enrolment, school feeding and child protection/child rights. Consultant(s) will present a detailed study design in the inception report, which will be finalised in consultation with Save the Children’s team.

The Consultant will develop a comprehensive study matrix based on the evaluation criteria and the project result framework. The table below presents the impact and outcome indicators and potential data collection sources.

Table 1: Impact and outcome indicators and potential data collection sources

| Expected Results | Indicators | Source |
| --- | --- | --- |
| Impact indicator | Primary school completion rate in target states (disaggregated by gender, disability, state) | Enrolment records Ministry of Education Statistical Books on Education – 2023 -2025 Annual Program review Project monitoring reports |
| Girls and boys in Sudan realize their right to quality, safe and inclusive primary education in a protective environment |  |  |
| Create a safer, protective and enabling learning environment for vulnerable girls and boys, including children living with disabilities, IDPs, refugees and children out of school | % and # of children (disaggregated by gender, vulnerable groups, and locality) attending school % and # children enrolled and completing the programs in ALP centres and catch-up classes (disaggregated by gender, vulnerable groups, and locality) | EMIS data / Rapid survey School records Monitoring reports that include Learning competencies survey and final tests ALP classes enrolment list/ roster. Class attendance sheets Pre- and post-training survey results. Class observation records Arabic and Math test records |
| Outcome 1 Improved access to inclusive, safe, protective, and quality primary formal and non-formal education services for vulnerable boys and girls | 1.1 % of enrolment of children in target schools and non-formal education centres (disaggregated by gender, disability, state, formal/non-formal education) | Enrolment records. Ministry of Education (MoE) Statistical Books on Education Sector |
| Outcome 2: Improved availability and access to nutritious food for students in both formal and non-formal education, using locally produced food items | 2.1 # of girls and boys in target schools and non-formal education centers who ate from more than 4 food groups in the last school week (disaggregated by disability) | Baseline, mid and endline and Observations on school days to observefood intake at school during the week) |
| Outcome 3: Improved access to quality preventive and responsive protection services for girls and boys, both in schools and communities | 3.1 – Indicator % Of boys and girls who report feeling safe and protected in target schools, non-formal education centers, and in the Child-Friendly Spaces/Multi-Purpose Activity Centers at the beginning and end of the project (disaggregated by gender, disability, and state) | Pre- and post-assessment results Endline: data collection from target schools, non-formal education centers, Child Friendly Spaces, MPACs (including number of children received case management disaggregated by gender) |
| Outcome 4: Increased realization of child rights through amplifying children’s voices and enhancing transparency and accountability in the delivery of essential basic and social services | 4.1 % of children and adults in the community believe that implementing child rights and banning corporal punishment in schools is beneficial for the community | Baseline, mid and endline |

5.2 Sampling

For the sampling section, study combines probability sampling for quantitative components and purposive sampling for qualitative components. This approach ensures statistical representativeness for key indicators while also capturing deeper context-specific insights on inclusion, quality, and implementation fidelity.

For quantitative sampling, a multi-stage cluster sampling approach will be reflected, ensuring that results are representative of the project population consistent with EU standards for credible evidence.  Disaggregation should be clearly applied by gender, age, disability status, displacement status, and other vulnerability dimensions, noting that vulnerability has an important intersectionality lens given the focus on the most vulnerable children.

For sample size calculation, use of the following parameters is recommended:

- 95% confidence level.

- 5–7% margin of error

Also, to follow the standard proportion-based formula as follows:

n0 = (Z² × p × (1−p)) / e²

Where Z = 1.96, p is the expected proportion for the key impact indicator (baseline/target, or 0.5 if unknown), and e is the margin of error.

The sample will then be adjusted using finite population correction:

n = n0 / [1 + (n0−1)/N]

And adjusted for clustering and non-response:

final = (n × DEFF) / (1−NR)

For qualitative sampling, purposive and criterion-based sampling should be reflected, ensuring inclusion of key stakeholder groups.

## Data Sources and Data Collection Methods / Tools

A desk review will be conducted using secondary data sources, viz, project documents, counterpart data, Baseline report, KAP survey report, primary education barriers in Sudan assessment report, SCI partners report on primary education, general education statistics in Sudan, and child protection reports from different clusters and partners. The study team will undertake the desk review exercise before field data collection.

All primary data collected during the study must facilitate disaggregation by gender, age, [disability, location or remoteness, vulnerability status]. Primary data collection will be undertaken by the recruited Consultant(s) and their research team including enumerators. For primary data collection, the team will undertake a survey with project beneficiaries using a standard questionnaire. Qualitative data collection will be undertaken by conducting FGDs and KIIs with relevant stakeholders including caregivers, children, community leaders and government officials.

The study team is required to adhere to Save the Children’s Safeguarding Policy, which consolidates three previous policies—Child Safeguarding, PSEAH (Protection from Sexual Exploitation, Abuse and Harassment), and Modern Slavery and Human Trafficking—into one comprehensive document, and the Data Protection and policies throughout all project activities.

The following data collection tools are recommended, however, the final tools will be decided in agreement with the Consultant(s).

Focus Group Discussions

- Target Groups:, Community leaders, Teachers, Caregivers, PTAs, MGs, Parents of children with disabilities (CwD), Community Child Protection Networks, Community based Transparency and Accountability Committees, and Girls & Boys (of different age cohorts). Child-friendly tools must be used for data collection with children.

- Objective: Gather diverse perspectives on the study faced by vulnerable groups, host communities, returnee or any other groups who benefited from project intervention through face-to-face group discussion and direct observation.

- Approach: Use structured focus group discussion guide. Ensure privacy, accessibility, and sensitivity. Facilitators will be trained to handle sensitive topics appropriately and taking into account gender consideration.

- Key Informant Interviews

- Target Groups: Project staff, government officials, project partners, humanitarian partners, Education officials, Headteachers, Teachers, and Community leaders, Social workers

- Objective: Obtain in-depth insights into personal, social, and institutional perspectives on the unique challenges faced by children in accessing education. Approach: Semi-structured interviews with open-ended questions. Special attention will be given to ensuring a safe and comfortable environment for respondents, accommodating their specific needs.

- Survey Questionnaire:

- Target Group: Households with school-age children who attend ALP program and/or catch up classes, IDP/displaced households and households with children with disabilities (CWD) and other vulnerable groups

- Approach: Structured questions for quantitative analysis

These tools are designed to gather comprehensive data from multiple stakeholders to inform targeted, context-specific interventions for enhancing inclusive and equitable education access in Sudan.

## Ethical Considerations

It is expected that this study will be:

- Child participation. Where appropriate and safe, children should be supported to participate in the evaluation process beyond simply being respondents. Opportunities for collaborative participation could include involving children in determining success criteria against which the project could be evaluated, supporting children to collect some of the data required for the evaluation themselves, or involving children in the validation of findings. Any child participation, whether consultative, collaborative or child-led, must abide by the 9 Basic Requirements for meaningful and ethical child participation.

- Inclusive. Ensure that children from different ethnic, social and religious backgrounds have the chance to participate, as well as children with disabilities and children who may be excluded or discriminated against in their community.

- Ethical: The study must be guided by the following ethical considerations:

  - Safeguarding – demonstrating the highest standards of behavior towards children and adults.

  - Sensitive – child rights, gender, inclusion and cultural contexts.

  - Openness - of information given to the highest possible degree to all parties involved.

  - Confidentiality and data protection - measures will be put in place to protect the identity of all participants and any other information that may put them or others at risk.

  - Public access - to the results when there are no special considerations against this

  - Broad participation - the relevant parties should be involved where possible.

  - Reliability and independence - the study should be conducted so that findings and conclusions are correct and trustworthy.

It is expected that:

- Data collection methods will be age and gender appropriate.

- Study activities will provide a safe, creative space where children feel that their thoughts and ideas are important.

- A risk assessment will be conducted that includes any risks related to children, young people’s, or adult’s participation.

- A referral mechanism will be in place in case any child safeguarding or protection issues arise.

- Informed consent will be used where possible.

# Expected Deliverables

The study deliverables and tentative timeline (subject to the commencement date of the study) are outlined below. The study team lead and SC study Project Manager will agree on final milestones and deadlines at the inception phase.

Deliverables and Tentative Timeline

| Deliverable / Milestones | Timeline |
| --- | --- |
| Final ToR to be submitted to the EUD for approval | 13th March 2026 |
| Feedback from EUD on the ToR | 27th March 2026 |
| Advertise the Final Evaluation Assignment | 29th March 2026 |
| Deadline for Receipt of Proposals from Consultants | 09th April 2026 |
| Contracting of Consultant and commencing of work | 19th April 2026 |
| Consultant to submit an inception report* in line with the provided template, including: - Final Evaluation objectives, scope and key study questions - Description of the methodology, including design, data collection methods, sampling strategy, data sources, and study matrix against the key study questions, draft tools - Data analysis and reporting plan - Caveats and limitations of study - Risks and mitigation plan - Ethical considerations including details on consent - Stakeholder and children communication and engagement plan - Key deliverables, responsibilities, and timelines - Resource requirements - Secondary data review and analysis | 29th April 2026 |
| Commenting of inception report including secondary review and draft tools for finalisation | 6th May 2026 |
| Final data collection tools (in the report language) and translation of the tools. | 13th May 2026 |
| Approval of the data collection tools and Ethical approval from HAC (state & federal). | 20th May 2026 |
| Finish Training of enumerators for data collection (trainings on safeguarding, data collection, consent forms and data protection signed, pretest by consultant) | 21st – 23rd May 2026 |
| Data collection | 24th May – 24th June 2026 |
| A Draft Final Evaluation Report including below elements: All reports are to use the proposed Save the Children Final Study Report template [unless another format is required by the project donor or used by partner who did the final evaluation]. - Executive summary - Background description of the project and context relevant to the Final Evaluation - Scope and focus of the Final Evaluation - Overview of the Final Evaluation methodology and data collection methods, including a Final Evaluation matrix - Findings aligned to each of the key Final Evaluation questions - Specific caveats or methodological limitations of the Final Evaluation - Conclusions outlining implications of the findings or learnings - Recommendations - Annexes (Project log frame, Final Evaluation ToR, Inception Report, Study schedule, Tools used, List of people involved) | 09th July 2026 |
| Consolidated feedback from key stakeholders will be provided by Save The Children within [2] weeks of the submission of the draft report. | 23rd July 2026 |
| Workshop to clarify feedback, and validation of the final findings and recommendations post addressing feedback received from Save the Children | 29th July 2026 |
| Data and analyses including all encrypted raw data, databases and analysis outputs | 6th August 2026 |
| Final Evaluation Report* incorporating feedback from consultation on the Draft Evaluation Report | 6th August July 2026 |
| Knowledge translation materials: - PowerPoint presentation of Study findings - Evaluation Brief** | 6th August 2026 |

*All reports are to use the Save the Children Final Study Report template. Please also refer to Save the Children technical writing guide.

** The Evaluation Brief is a 2-4 pages summary of the full report and will be created using the Save the Children template.

All documents are to be produced in MS Word format and provided electronically by email to the SC Evaluation Project Manager. Copies of all PowerPoint presentations used to facilitate briefings for the project should also be provided to Save the Children in editable digital format.

# FINAL EVALUATION Management

The final evaluation will be overseen by a multidisciplinary team to ensure that the process is conducted in a rigorous, transparent, and professional manner. The study management structure will include representatives from Supply, Program Implementation, Program Development, Quality and Impact (PDQ), and the MEAL team. These members will contribute to different aspects of the evaluation process, including coordination, logistical support, technical oversight, data quality assurance, and review of evaluation outputs.

The following table details the different deliverables, responsible person, timeline and support functions:

| Deliverables | Responsible | By when | Supporting role |
| --- | --- | --- | --- |
| Final Evaluation tender submission/posting | Supply Chain | 29 March 2026 | Supply Chain Manager/MEAL |
| Tender review, selection of study team and contracting | MEAL Manager | 19 April 2026 | Outcome Manager, Senior Learning & Evidence Specialist, MEAL, Chief of Party |
| Inception report | Consultant | 29 April 2026 |  |
| Review of the inception report | Senior learning & evidence specialist | 6 May 2026 | Outcome Manager, Senior Learning & Evidence Specialist, MEAL, Chief of Party, Technical Specialists/Advisors |
| Finalisation of Data collection tools | Consultant | 13 May 2026 | Outcome Manager, Senior Learning & Evidence Specialist, MEAL, Chief of Party, Technical Specialists/Advisors |
| Ethics submission | Consultant | 13 May 2026 | MEAL Manager and Senior Learning & Evidence Specialist, |
| Logistical arrangements | MEAL Manager | 20 May 2026 | SC Logistical support/MEAL/Chief of Party, Outcome Manager, Field program team |
| Data collection | Consultant | 24th May -24th June 2026 | MEAL staff to facilitate the process in different states |
| Data management and analysis (coding, transcriptions, data cleaning, integration and analysis) | Consultant | 30 June 2026 | MEAL Manager and Senior Learning & Evidence Specialist, |
| Draft Final Evaluation Report | Consultant | July 2026 | MEAL Manager and Senior Learning & Evidence Specialist, |
| Review of Draft Final Evaluation Report and providing feedback | Senior Learning and Evidence Specialist and MEAL Manager | 23 July 2026 | Outcome Manager, Chief of Party, Technical Specialists/Advisors. |
| Workshop to clarify feedback on draft report and final validation of findings/ recommendations | Senior Learning and Evidence Specialist and MEAL Manager | 29th July 2026 | Senior Learning and Evidence Specialist, MEAL Manager, Outcome Manager, Chief of Party, Technical Specialists/Advisors. |
| Final study report and submission of data and analyses | Consultant | 6th August 2026 | Senior Learning and Evidence Specialist, Research Manager, and MEAL Manager and Technical Specialist/advisors |
| Knowledge translation materials | Senior Learning & Evidence Specialist | 6th August 2026 | Technical Advisors, Research Manager, |
| Project team meeting to develop Study Response Plan | MEAL Manager, Senior Learning & Evidence Specialist | 6th August 2026 | Chief of party, Outcome Managers |
| Study final report (together with response plan) posted on OneNet and reviewed | Senior learning & evidence specialist | 13th August 2026 | Research Manager |

# Study Team and Selection Criteria

### Understanding of Requirements and Experience

To be considered, the study team members together must have demonstrated skills, expertise and experience in:

- Designing and conducting Final evaluations using the proposed design

- Conducting studies in the field of multisectoral program with a focus on education, particularly in relation to basic education, child protection, and child rights governance

- Leading socio-economic research, evaluations or consultancy work in Sudan that is sensitive to the local context and culture, particularly child rights, gender equality, ethnicity, religion and minority groups, disability and/or other factors.

- Conducting ethical and inclusive studies involving children and children’s participatory techniques

- Conducting ethical and inclusive studies involving marginalised, deprived and/or vulnerable groups in culturally appropriate and sensitive ways

- Managing and coordinating a range of government, non-government, community groups and academic stakeholders

- Experience conducting study in humanitarian contexts

- Sound and proven experience in conducting evaluations based on EUD evaluation criteria, particularly utilisation and learning focused evaluations

- Extensive experience of theories of change and how they can be used to carry out evaluations

- Strong written and verbal skills in communicating technical and/ or complex findings to non-specialist audiences (especially report writing and presentation skills)

- A track record of open, collaborative working with clients

There is a high expectation that:

- Members (or a proportion) of the study team have a track record of previously working together.

- A team leader will be appointed who has the seniority and experience in leading complex study projects, and who has the ability and standing to lead a team toward a common goal.

- The team could commit to the terms of the project and have adequate and available skilled resources to dedicate to this study over the period.

- The team has a strong track record of working flexibly to accommodate changes as the project is implemented.

To apply for this study, applicants are expected to share the following documents:

- A proposal showing your understanding of the assignment and how you will conclude the work, including proposed methodologies, mode of analysis, and the number of personnel involved, detailed timelines, budget, and any foreseen challenges.

- Up to date organizational/individual Consultant CVs and CVs for relevant staff.

- Cover letter.

- Traceable and contactable referees for each.

- Two sample reports from previous most recent education consulting projects (all samples will be kept confidential) or links to website where reports can be retrieved (highly recommended).

### Financial Proposal

Save the Children seeks value for money in its work. This does not necessarily mean "lowest cost", but quality of the service and reasonableness of the proposed costs. Proposals shall include personnel allocation (role / number of days / daily rates / taxes), as well as any other applicable costs.

# Schedule of Payment

The following payments will be made to the consultant using and agreed mode of payment. SCI can adjust the payment schedule based on opportunity and negotiation with the contractor. However, it is recommended to avoid payments upon contract signature unless the consultants request it for covering consistent expenses for the inception phase; and to leave the instalment corresponding to the last trance to a consistent proportion, to incentivise the evaluation team to satisfactorily address report improvement requests].

- Upon approval of inception report and tools: [20%]

- Upon submission of First Draft study Report: [30%]

- Upon approval of final study report: [50%]

# HOW TO APPLY

If interested in applying for this study, please refer to the Consultant EOI Form.

Contact persons for this evaluation are:

- Abbas Boach, the MEAL Manager, abbas.boach@savethechildren.org and

- Akram Abdelgayoum, Senior Learning and Evidence Specialist, akram.abdelgayoum@savethechildren.org

# Annexes

Annex 1: Project Log-frame – desk review

Annex 2: List of project documents to be consulted - desk review

Annex 3: SC Steering Committee Roles and Responsibilities – desk review

Annex 4: SCI Safeguarding Policy

Annex 5: SCI Study matrix for the study

Annex 6: SCI Evaluation Scoring for perspective consultants

| Category | Evaluation Quality Criteria (used for internal scoring after completion) |
| --- | --- |
| Purpose, Design and Methods | 1. Does the evaluation report clearly identify the evaluation's purpose (including its key objectives, questions and criteria) as set out in the evaluation's Terms of Reference (ToR)? |
|  | 2. Are the data collection and analysis methods a clearly justified approach to addressing the evaluation's purpose and questions? (Do they provide valid, reliable and ethical data?) |
|  | 3. Is the methodology suitably tailored to the context and population groups to which the evaluation questions relate (e.g. re gender, disability, socio-economic status, geographic location, cultural context, ethnicity)? |
|  | 4. Are the size and composition of the sample in proportion to the conclusions sought by the evaluation? |
|  | 5. Does the evaluation build on what is already known, for example existing tried and tested frameworks and tools, existing data/evidence, and previous lessons learned? |
|  | 6. Are the methods used to collect and analyse data and any limitations of the quality of the data and collection methodology explained and justified? |
|  | 7. Has any personal and professional influence or potential bias among those collecting or analysing data been recorded and addressed or mitigated ethically? |
| Analysis and Findings | 8. If evaluating impact, is a point of comparison used to show that change has happened (e.g. a baseline, a counterfactual, comparison with a similar group)? |
|  | 9. Is the explanation of how (e.g. theory of change, logframe, activities) the intervention contributes to change explored? |
|  | 10. Is the data well triangulated, such as by using different data collection methods, types of data and stakeholder perspectives? |
|  | 11. Are alternative factors (eg. the contribution of other actors) considered to explain the observed result alongside an intervention’s contribution? |
|  | 12. Are unintended and unexpected changes (positive or negative) identified and explained? |
|  | 13. Are the perspectives of children & communities included in the evidence, including the most deprived and marginalised? Note: For evaluations focused on young children, caregiver perspectives are adequate instead. |
|  | 14. Are the findings disaggregated according to sex, disability and other relevant social differences? |
|  | 15. Is there a clear logical link between the data that was collected and analysed, and the conclusions and recommendations presented? |
|  | 16. Are conflicting findings and divergent perspectives presented and explained in the analysis and conclusions? |
|  | 17. Are the findings and conclusions of the assessment shared with and validated by a range of key stakeholders (e.g. communities, partners, Save the Children staff)? |
| Communication and Use | 18. Is the analysis and interpretation of the data well communicated through accessible language and helpful visuals (diagrams, graphs, tables as needed)? |
|  | 19. Are references, annexes and links included that provide additional relevant data, analysis or references (including key documents and which individuals/stakeholders were involved)? |
|  | 20. Is there a clear plan for how to use the results, including recommendations that are 'SMART' (Specific, Measurable, Achievable, Relevant, Timebound) and directed toward the appropriate 'end users', a dissemination plan, and specific actions for implementing these recommendations? |

Please note, the evaluation quality criteria above are all the external consultants will need to be aware of.

| ToR prepared by: | Abbas Ibrahim Bosch – EUD MEAL Manager |
| --- | --- |
| ToR approved by: |  |
| Date of sign off: |  |