TERMS OF REFERENCE

ECHO Health & Nutrition 2025-2026

Endline Study

To improve access to essential healthcare and nutrition services for conflict-affected populations and provide emergency assistance in response to sudden-onset crises in Sudan

# Project Summary

| Type of evaluation: | Endline (cross-sectional, mixed-methods, KAP-focused) |
| --- | --- |
| Name of the project: | SDN_ECHO_H&N-CM_2025-2026 |
| Project Start and End dates: | Start date: 1st May 2025 End date: 30th April 2026 |
| Project duration: | 11 months, 30 days |
| Project locations: | Sudan: North Darfur (Tawila), Khartoum (Omdurman) |
| Thematic areas: | Health, Nutrition, GBV (medical response), DRR/CM |
| Donor: | ECHO |
| Key stakeholders | Local partner: APDHWO/ MOH |
| Overall objective of the project: | Reduce M/NCH morbidity & mortality; treat/prevent acute malnutrition; enable rapid crisis response |

- Background

  - Context information:

Sudan continues to face severe and compounding humanitarian and development challenges following the outbreak of conflict in April 2023 between the Sudanese Armed Forces (SAF) and the Rapid Support Forces (RSF). The escalation of violence has resulted in widespread civilian harm, large-scale displacement, and the collapse or disruption of essential public services. More than 10 million people have been displaced, while millions more experience restricted access to food, water, health care, cash, and basic social services.

In response to these needs, Save the Children (SC), in partnership with Anhar for Peace, Development and Humanitarian Work Organization (APDHWO), has been implementing an integrated health and nutrition project targeting conflict-affected, displaced, and highly vulnerable communities, including IDPs, refugees, and host populations, in North Darfur (Tawila locality) and Khartoum (Omdurman). The project aims to enhance equitable access to inclusive, gender-sensitive, and high-quality primary health care (PHC) and nutrition services through a community-centred approach.

The Action supports five health facilities (three in North Darfur and two in Khartoum) to deliver lifesaving services for women of reproductive age, particularly pregnant and lactating women (PLW), and children under five. Interventions include maternal and child health care, strengthened immunization systems, consistent availability of essential medicines, and functional referral pathways. Nutrition services are delivered through the Community-Based Management of Acute Malnutrition (CMAM) model, including Outpatient Therapeutic Programs (OTP), Targeted Supplementary Feeding Programs (TSFP), and Infant and Young Child Feeding in Emergencies (IYCF-E) counselling across community, PHC, and stabilization centre levels.

The project also seeks to transform community norms and behaviours through behaviour change communication (BCC), while strengthening the capacity of local health teams (LHTs), healthcare providers, and Community Nutrition Volunteers (CNVs). The Action incorporates a Crisis Modifier mechanism to enable early response to verified alerts and tailor interventions to evolving needs, vulnerabilities, and contextual constraints.

- Purpose of the Endline Study

The overall purpose of the endline study is to assess project performance, outcomes, and emerging contribution to improved access, utilization, quality, and equity of health and nutrition services in the target locations. The endline will compare final values with baseline findings, routine monitoring data, and project targets, while generating evidence on effectiveness, relevance, inclusion, accountability, sustainability, and lessons learned. Specifically, the study aims to:

- Establish endline values and compare progress: Measure endline values for key performance indicators across the Health, Nutrition, and Crisis Modifier result areas and compare them with baseline values and project targets, disaggregated by state, sex, age, disability, and population group where feasible.

- Assess changes in Knowledge, Attitudes, and Practices (KAP): Examine changes in community-level KAP related to maternal and newborn health, sexual and reproductive health (SRH), child health, GBV response, and nutrition practices (IYCF-E and CMAM), and assess the extent to which BCC and community engagement approaches contributed to improved behaviours.

- Assess access, quality, equity, and service readiness: Examine changes in service availability, accessibility, acceptability, quality, and equity across project-supported facilities, including whether women, adolescents, persons with disabilities, IDPs/refugees, and host communities were reached equitably.

- Generate learning and accountability evidence: Document lessons learned, unintended effects, community perceptions, AAP performance, and actionable recommendations to inform future health and nutrition programming in similar conflict-affected settings.

II. Study Methodology

The endline will apply a cross-sectional, mixed-methods design, integrating quantitative and qualitative approaches to assess outcomes and compare change against baseline values. The approach will be grounded in the KAP framework and complemented by access, quality, equity, accountability, and contribution-analysis lenses. Where possible, the endline methodology, tools, sampling approach, and indicator definitions should mirror the baseline to ensure valid comparison.

a. Type of Study:

Quantitative Component

- Administer structured household surveys to measure endline KAP related to PHC, maternal and child health, GBV referral awareness, nutrition, and IYCF-E.

- Measure service utilization patterns, barriers to care, satisfaction, and accountability experiences.

- Assess nutrition-related practices and screening/referral experiences among households with children under five.

- Conduct facility assessments to measure current service readiness, availability of essential medicines, staffing, supplies, IPC, referral pathways, and nutrition service functionality.

- Review routine service records to measure indicators that require implementation data, including CMAM admissions, recovery/defaulting, stock status, and crisis response timeliness.

Qualitative Component

- Conduct KIIs and FGDs to explore perceived changes in service quality, health-seeking behaviour, trust in services, barriers and enablers, and community perceptions of the project.

- Explore gender-related, disability-related, safety-related, and access-related factors affecting utilization of health and nutrition services.

- Document lessons learned, good practices, sustainability considerations, and recommendations from communities, health workers, CNVs, local authorities, MoH, and project teams.

Triangulation and Contribution Analysis

Endline findings will be triangulated across household data, facility assessments, service records, qualitative evidence, routine monitoring, and baseline findings. The study will use contribution analysis to assess the plausible contribution of the project to observed changes, recognizing the influence of conflict, displacement, access constraints, and other contextual factors.

b. Units of Analysis

- Demand-Side (Community Level)

- Households and caregivers of children under five

- Pregnant and Lactating Women (PLW)

- Adolescents (male and female), where culturally appropriate

- Persons with disabilities, using self-reported functional difficulty questions where feasible

Supply-Side (Service Delivery Level)

- Primary Health Care Centres (PHCCs): service readiness, staffing, quality, and continuity of care

- Community Health Workers (CHWs) and Community Nutrition Volunteers (CNVs): outreach effectiveness, case finding, and behaviour change support

- Technical and managerial stakeholders, including MoH representatives, facility in-charges, local authorities, community leaders, and partner NGOs

c. Geographic Scope

The endline will cover the project catchment populations in North Darfur (Tawila locality) and Khartoum (Omdurman locality), representing both conflict-affected and urban implementation contexts. The study will cover all five project-supported PHCCs: three in North Darfur and two in Khartoum.

d. Rationale for the Design

The cross-sectional mixed-methods design is appropriate for measuring endline status and comparing results against baseline values while remaining feasible in insecure and hard-to-reach locations. By combining household, facility, routine service, and qualitative data, the design will assess changes in community-level behaviours and demand-side barriers alongside service readiness and quality. The approach will also ensure that gender, age, disability, population status, and geographic differences are reflected in the analysis.

- KAP Framework and Analytical Lenses

The Knowledge–Attitudes–Practices (KAP) framework will guide endline tool development and analysis to measure changes in community knowledge, beliefs, and behaviours related to MNCH, SRH, GBV response, and nutrition (IYCF-E/CMAM). The KAP framework will be complemented by Access, Quality, Equity, AAP, and Contribution Analysis lenses to interpret whether observed changes are linked to project interventions and whether services were inclusive, acceptable, and accountable.

| Domain | Key Focus Areas | Example Endline Questions | Purpose / Use |
| --- | --- | --- | --- |
| Knowledge | Awareness of pregnancy danger signs, ANC/PNC schedules, skilled birth attendance, GBV referral timing, child health, immunization, IYCF-E and CMAM. | What pregnancy danger signs do you know? What should a GBV survivor do within 72 hours? What foods should a child under two eat for healthy growth? | Measures change in awareness and factual understanding compared with baseline. |
| Attitudes | Perceived benefits and barriers to using services; trust in health workers; norms around GBV disclosure, breastfeeding, contraception, and child feeding. | Do you agree that facility delivery is safer than home delivery? Do you trust health workers to provide confidential care? | Assesses changes in beliefs, norms, and motivation to seek care. |
| Practices | Actual health-seeking for ANC/PNC, child illness, GBV care, use of PHCCs/CHWs/CNVs, feeding, hygiene and newborn care practices. | Where did you seek care when your child was sick? Did you exclusively breastfeed for six months? Did you use nutrition services when needed? | Identifies behavioural changes and remaining practice gaps. |
| Access, Quality & Equity | Distance, cost, safety, disability access, respectful care, confidentiality, satisfaction, complaint mechanisms, and inclusion. | Were services affordable and respectful? Were disability or gender-specific needs addressed? Did you know how to provide feedback or complaints? | Assesses whether service improvements were equitable, inclusive, and accountable. |

2.1 Indicators Covered

Health (Result 1):

- Endline coverage and utilization of ANC, PNC, skilled birth attendance, child health and immunization services, compared with baseline where applicable.

- Changes in community knowledge and practices related to MNCH, SBA, child illness care-seeking, GBV-sensitive referral awareness, and quality perceptions.

- Current facility readiness, availability of essential medicines and supplies, staffing, IPC, referral systems, and GBV-sensitive care capacity.

- Routine service record indicators, including GBV clinical care indicators were ethically and operationally appropriate.

Nutrition (Result 2):

- Endline IYCF-E practices, including exclusive breastfeeding, complementary feeding, dietary diversity, and feeding during illness.

- Community awareness of malnutrition signs and care-seeking pathways.

- CMAM service functionality, staffing, supplies, CNV outreach effectiveness, and IYCF-E counselling.

- SAM/MAM admissions, recovery/defaulting, and RUTF/RUSF stock status using routine records and project monitoring data.

Crisis Modifier (Result 3):

- Extent to which affected populations were reached within agreed response timeframes following verified alerts.

- Community perceptions of rapid support, timeliness, relevance, and adequacy.

- Use of crisis modifier assessment findings and adaptation of support to contextual needs.

2.2 Data Sources and Tools

| Data Source | Method/Tool | Purpose |
| --- | --- | --- |
| Household Survey (KAP) | Structured questionnaires for caregivers/PLW; adolescent module optional | Measure endline KAP and compare with baseline values. |
| Facility Assessment | Service readiness checklist covering GBV capacity, BeMONC, WASH/IPC, cold chain, medicines, supplies, staffing and referrals | Assess current functionality, quality and readiness of supported facilities. |
| Registers/Records Review | ANC, delivery, OPD, GBV/CMR, pharmacy, CMAM, EWaRN and crisis modifier records | Measure implementation-based indicators and validate reported results. |
| Qualitative Inquiry | KIIs and FGDs with MoH, facility staff, CNVs, community leaders, women, caregivers, adolescents and persons with disabilities | Explore perceived changes, barriers, enablers, quality, sustainability and lessons learned. |
| AAP & Feedback Mechanisms | Perception survey and review of feedback/complaints data | Assess accountability, inclusiveness, responsiveness and community satisfaction. |

2.3 Sampling Strategy

The endline will use a multi-method sampling approach aligned as closely as possible with the baseline design. For the household survey, a two-stage cluster sampling approach will be used, selecting clusters proportionally to population size and households systematically within selected clusters. A sample of approximately 200 households per state (around 400 overall) is recommended to support comparison with baseline values while remaining feasible in insecure and hard-to-reach contexts. The survey will target caregivers of children under five and pregnant or lactating women, with data disaggregated by sex, age, disability and geography.

All five project-supported PHCCs will be assessed through a facility census. A purposive sample of iCCM or community outreach sites may be included where relevant. For the qualitative component, approximately 6–8 KIIs and 3–4 FGDs per state will be conducted with health officials, facility staff, CHWs/CNVs, GBV focal points, community leaders, caregivers, and community members, including persons with disabilities where feasible.

2.4 Data Collection and Quality Assurance

a. Digital Data Collection:

Data will be collected using KoBoToolbox or ODK on tablets, with real-time validation, skip logic, unique identifiers, and GPS stamping where safe and appropriate. Offline forms may be used where connectivity or security conditions require.

b. Enumerator Training and Piloting:

Enumerators and supervisors will receive training covering research ethics, informed consent, safeguarding, GBV sensitivity, disability inclusion, referral protocols, endline indicator definitions, tool piloting, and data quality procedures.

c. Quality Control Measures:

- Daily review of submissions by supervisors and MEAL focal points.

- 10% back-checks and 5% spot-checks, where feasible and safe.

- Automated error detection, range checks, skip logic, and consistency checks.

- Random verification of sampled clusters and review of routine service records.

d. Ethical Considerations:

- Informed consent/assent obtained for all participants.

- Confidentiality strictly maintained and no identifiable sensitive data disclosed.

- GBV referral pathways activated where disclosures occur.

- Procedures aligned with Do No Harm, SCI safeguarding principles, and conflict-sensitive data collection practices.

2.5 Data Analysis

Quantitative Analysis:

- Descriptive statistics, frequency distributions, and 95% confidence intervals.

- Baseline-to-endline comparison for comparable indicators, including absolute and percentage-point changes.

- Indicator-specific calculations for health, nutrition, AAP, and crisis modifier results.

- Disaggregation by sex, age, disability, geography, and population group where feasible.

- Weighted estimates to adjust for cluster sampling where appropriate.

Qualitative Analysis:

- Thematic coding guided by KAP domains, access, quality, equity, accountability and contribution-analysis themes.

- Triangulation with quantitative findings, routine monitoring data, facility records, and baseline findings.

- Identification of lessons learned, sustainability factors, and practical recommendations.

2.6 Data Triangulation and Validation

Preliminary findings will be triangulated across household surveys, facility assessments, registers, routine monitoring data, qualitative evidence, and baseline values. A validation workshop will be conducted with project teams, MoH, partners, and community representatives to review findings, confirm interpretations, and agree on learning and recommendations for future programming.

2.7 Deliverables

- Inception Report: Detailing endline methodology, sampling, tools, indicator matrix, analysis plan, work plan, and ethical considerations.

- Clean Datasets & Codebooks: Household, facility, routine records, CMAM, AAP and qualitative data files where applicable.

- Endline Report: Including endline indicator values, comparison with baseline and targets, 95% confidence intervals where applicable, KAP analysis, equity analysis, contribution analysis, lessons learned, and recommendations.

- Presentation/Brief: Key findings, infographics, updated IPTT/endline indicator table, and learning summary for dissemination.

2.8 Roles and Responsibilities

Save the Children (MEAL team) will be responsible for overall coordination and technical oversight of the endline study, including review of methodology, tools, sampling, data quality protocols, analysis outputs, and final reporting. Local Partners and the Ministry of Health (MoH) will support field coordination, community entry, access facilitation, and validation of findings. The consultant/research team will lead data collection, data cleaning, analysis, and report drafting while ensuring adherence to ethical standards, safeguarding, conflict-sensitive protocols, and agreed quality assurance measures throughout the study.

2.9 Timeline: Indicative – 6 Weeks

| Phase | Activities | Duration | Payment |
| --- | --- | --- | --- |
| Week 1 | Inception, document review, tool adaptation, work plan, ethical approvals and pilot | 1 week | 30% |
| Weeks 2–3 | Field data collection: household survey, facility assessment, records review and qualitative inquiry | 2 weeks |  |
| Week 4 | Data cleaning, validation, preliminary analysis and baseline-endline comparison | 1 week |  |
| Week 5 | Draft report, validation workshop and incorporation of feedback | 1 week | 30% |
| Week 6 | Final report, presentation, dissemination and learning session | 1 week | 40% |

2.10 Code of Conduct

Save the Children’s work is based on deeply held values and principles of child safeguarding, and it is essential that all people working for and with Save the Children demonstrate commitment to children’s rights and humanitarian principles. The consultant will be required to sign and abide by Save the Children’s Code of Conduct and safeguarding policies.

A contract will be signed by the consultant before commencement of the assignment. The contract will detail the terms and conditions of service, inputs, deliverables, timeline, and payment schedule. The consultant will treat all information disclosed during the assignment as private and confidential and will not disclose or publish any information without prior written consent from Save the Children. Sensitive information, particularly concerning individual children, survivors, or vulnerable participants, must be treated as strictly confidential. Any corrupt, unethical, or safeguarding-related violation may render the consultancy agreement void.

2.11. Study Kick-off and Field Coordination

SCI/MEAL team will organize the study kick-off meeting before the start of data collection to agree on the study timeline, methodology, roles, communication channels, and field coordination arrangements.

The consultant is expected to closely coordinate with the MEAL teams in the four states where data will be collected. The consultant should also share an online data collection tracker and keep it regularly updated and accessible to the MEAL team.

Given the conflict-sensitive context, the consultant must remain in close follow-up with the MEAL team throughout the fieldwork. Any local authority requirements, including permits or approvals, should be reviewed and cleared by the MEAL Manager in each state before proceeding

3. Consultant Profile

- Proven experience in quantitative and qualitative endline evaluations or outcome assessments, preferably in health, nutrition, child protection, GBV, or humanitarian programming; applicants should submit two relevant reports as evidence.

- Broad knowledge of humanitarian and development issues, specifically health, nutrition, gender, livelihoods, child protection, and accountability in fragile contexts.

- Demonstrated experience in KAP studies, mixed-methods evaluation, facility assessments, routine records review, and baseline-to-endline comparison.

- Fluency in Arabic and English; excellent verbal and written communication skills and strong report writing capacity.

- Awareness of cultural sensitivities and local context, preferably with working experience in Sudan and conflict-affected settings.

- Ability to work with teams under pressure, manage field risks, meet deadlines, and produce high-quality deliverables.

To apply for this study, applicants are expected to share the following documents:

- A brief, 4-page proposal showing understanding of the assignment and how the work will be conducted.

- A budget in USD covering data collection, data analysis, reporting, validation and dissemination.

- Up-to-date organizational/individual consultant CVs.

- Cover letter.

- Traceable and contactable referees.

- Two relevant sample reports or links to websites where reports can be retrieved; all samples will be kept confidential.

Days

The data analysis and report writing are expected to take 7 days including weekends.

Payment Schedule

The payment shall be 33% upon submission of Inception Report and Tools, 33% upon submission of satisfactory Draft report, and 33% upon submission of a satisfactory final report. Preference will be given to Sudanese nationals/consultants.

APPLICATION PROCEDURES

The offer, comprising of a Technical and Financial Proposal, should be submitted and addressed as follows: Sudan CO procurement SudanCO.procurement@savethechildren.org. For any question/query relating to the proposal, please email janet.mugo@savethechildren.org.